## Instructions
i-Finance UAT Script
Admin (App 200) — Identity, Users, Roles, Platform Administration
Environment URL | (fill in: e.g. http://localhost:8080 or the deployed URL)
Build / version date | 2026-06-12 (Phase 4)
UAT round
Lead tester
Start date
End date
How to test
1. Each tab is one functional area. Work top-to-bottom; one row = one test case.
2. Follow the Steps column exactly; compare the outcome with Expected Result.
2b. Sample Data / Records tells you WHICH seeded record, account or value to use — prefer it over inventing your own so results are reproducible.
3. Set Status from the dropdown: Pass / Fail / Blocked / N/A.
4. On Fail or Blocked, ALWAYS fill Comments (what happened, screenshots reference, error text).
5. Fill Tested By + Test Date on every executed row.
6. Login accounts: use the quick-login buttons on the login page, or accounts provided by the admin. Never write passwords in this file.
7. Hard-refresh (Ctrl+F5) after the team deploys a fix before retesting.
Status legend
Pass | Works exactly as the Expected Result describes
Fail | Does not match the Expected Result (describe in Comments)
Blocked | Cannot be executed (missing data/role/dependency failed)
N/A | Not applicable to this round/role
Seeded UAT data (your starting point)
- 6 test accounts exist matching the quick-login buttons: ADMIN (SYS_ADMIN), HASHEM.ALKABBI (Director/approver), NASER.ALKHAJA, AYESHA.AMERI, SHAIKHA.GALAMERI, SHAIKHA.ALSUWAIDI (managers).
- Module roles: AYESHA = Petty Cash admin/approver, HASHEM = DT approver, NASER = DT finance, SHAIKHA.GALAMERI = HR manager, SHAIKHA.ALSUWAIDI = HR viewer.
Live summary
Functional area | Cases | Pass | Fail | Blocked | Executed %
Login & Session | 7
Dashboard | 4
My Workspace | 12
User Management | 8
Roles & Permissions | 5
Organisation | 3
System Administration | 9
Delegations & Announcements | 9
Shell & Platform | 7
Wave Enhancements | 19
Enhancement Round 2 | 13
TOTAL

## Login & Session
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ADMIN-LOG-01 | Login | Valid login | 1. Open the app URL 2. Enter a valid username + password (or use a quick-login button) 3. Click Sign In | Quick-login: System Admin (ADMIN) | Dashboard opens; top bar shows your name and avatar initials; side navigation matches your role
ADMIN-LOG-02 | Login | Invalid password | 1. Enter a valid username with a wrong password 2. Click Sign In | Username ADMIN + any wrong password | Error message 'Invalid credentials or account inactive'; stays on login page
ADMIN-LOG-03 | Login | Inactive account | 1. Login with a deactivated account (ask admin to deactivate a test user first) | Create + deactivate UAT.TESTER1 first (User Management) | Login refused with the same generic error
ADMIN-LOG-04 | Session | Refresh keeps session | 1. Login 2. Press F5 / Ctrl+F5 on any page | Quick-login buttons on the login page (ADMIN, HASHEM.ALKABBI, NASER.ALKHAJA…) | Still logged in; same page or dashboard reopens (no login prompt)
ADMIN-LOG-05 | Session | Deep link without session | 1. Logout 2. Open the app URL again | Quick-login buttons on the login page (ADMIN, HASHEM.ALKABBI, NASER.ALKHAJA…) | Login page shown; no app content visible before login
ADMIN-LOG-06 | Logout | Logout clears session | 1. Click your avatar (top-right) > Logout 2. Press Back in the browser | Quick-login buttons on the login page (ADMIN, HASHEM.ALKABBI, NASER.ALKHAJA…) | Returned to login; Back does not re-enter the app with data
ADMIN-LOG-07 | Login | Arabic login page | 1. On the login page switch language to AR (ع) 2. Login | Quick-login buttons on the login page (ADMIN, HASHEM.ALKABBI, NASER.ALKHAJA…) | Login page is mirrored (RTL) with Arabic labels; after login the app stays in Arabic

## Dashboard
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ADMIN-DSH-01 | Headline counts | Stats cards show live numbers | 1. Open Home/Dashboard 2. Compare 'Users' count with the Users list total |  | Cards show non-zero sensible numbers; users count matches the Users page total
ADMIN-DSH-02 | Charts | Both charts render | 1. Open Dashboard 2. Wait for charts to load |  | Approval cycle-time bar chart + 30-day activity line chart render with axes and legend; no empty boxes
ADMIN-DSH-03 | Charts | Charts survive navigation | 1. Open Dashboard 2. Navigate to Users, then back to Dashboard |  | Charts render again correctly (not blank, not duplicated)
ADMIN-DSH-04 | Loading states | Skeleton then data | 1. Hard-refresh (Ctrl+F5) on Dashboard |  | Brief skeleton/placeholder shown, then real data; no flash of errors

## My Workspace
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ADMIN-WSP-01 | My Profile | Profile loads current data | 1. Go to My Workspace > My Profile |  | Display names, email, phone, employee number, organisation are the CURRENT values from the server
ADMIN-WSP-02 | My Profile | Update phone persists | 1. Change Phone 2. Click Save Profile 3. Hard-refresh (Ctrl+F5) and reopen My Profile | Phone: +97150 000 1234 (restore the original after) | Success banner on save; after refresh the NEW phone is still shown
ADMIN-WSP-03 | My Profile | Update Arabic display name | 1. Edit Display Name (Arabic) 2. Save 3. Refresh and recheck |  | Arabic name saved and persists; shown RTL in the field
ADMIN-WSP-04 | My Profile | Employee number not lost | 1. Note your Employee Number 2. Change phone and Save Profile 3. Refresh |  | Employee Number is unchanged after a profile save
ADMIN-WSP-05 | My Profile | Upload photo | 1. Click Change Photo 2. Pick a JPG/PNG (any size) 3. Wait for upload | Any JPG/PNG photo file | File picker opens; avatar shows the photo; photo still there after Ctrl+F5
ADMIN-WSP-06 | My Profile | Replace photo | 1. Upload a different photo over the existing one |  | New photo replaces the old one without errors
ADMIN-WSP-07 | Change password | Happy path | 1. In Change Password enter a new valid password twice 2. Submit 3. Logout and login with the NEW password 4. Change it back |  | Success message; old password no longer works; new one does
ADMIN-WSP-08 | Change password | Validation | 1. Try mismatching passwords 2. Try a password shorter than 8 characters |  | Clear validation errors; nothing saved
ADMIN-WSP-09 | Notifications | List + unread badge | 1. Open Notifications 2. Compare the bell badge count with unread rows |  | List loads; badge equals the number of unread notifications
ADMIN-WSP-10 | Notifications | Mark as read | 1. Mark one notification as read |  | Row state changes; bell badge count decreases by 1
ADMIN-WSP-11 | Pending approvals | My queue | 1. Open Pending Approvals (use an approver account with pending items) |  | Only items waiting for YOUR approval are listed with module, requester, date
ADMIN-WSP-12 | Pending approvals | Approve / reject | 1. Approve one item 2. Reject another with a comment |  | Items leave the queue; requester gets a notification; status history updated

## User Management
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ADMIN-USR-01 | Users list | Server pagination | 1. Open Users 2. Check the pager caption (e.g. '1-50 of N') 3. Click next page |  | Counts are correct; next page loads different rows; pager updates
ADMIN-USR-02 | Users list | Search | 1. Type part of a name/username in search 2. Pause typing |  | List filters after a short delay (server search); count updates; clearing search restores the full list
ADMIN-USR-03 | Users list | Status filter | 1. Filter by Active, then Inactive |  | Only matching users shown each time
ADMIN-USR-04 | Create user | Happy path | 1. Click New User 2. Fill username, names, email, org, role(s), password 3. Save 4. Logout and login as the new user | Username UAT.TESTER1 · role PLATFORM_USER · org Finance Division | User created and appears in the list; new user can login and sees role-appropriate navigation
ADMIN-USR-05 | Create user | Duplicate username | 1. Create a user with an existing username | Existing username: NASER.ALKHAJA | Clear error; no duplicate created
ADMIN-USR-06 | Edit user | Change roles | 1. Edit a test user 2. Add/remove a role 3. Save 4. Login as that user | Test user UAT.TESTER1 — add/remove AUDITOR | Saved roles reflected; navigation/permissions change accordingly
ADMIN-USR-07 | Edit user | Edit fields | 1. Edit display names / email / phone / employee number / org 2. Save and reopen |  | All edited values persisted and shown
ADMIN-USR-08 | Deactivate | Deactivate + reactivate | 1. Deactivate a test user 2. Try logging in as them 3. Reactivate |  | Deactivated user cannot login; after reactivation they can

## Roles & Permissions
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ADMIN-ROL-01 | Roles list | Vault list renders | 1. Open Roles |  | Dark 'Vault' page lists roles with code, type, member count, active state
ADMIN-ROL-02 | Create role | New role | 1. Create a role with code + names 2. Save | Code UAT_ROLE1, name 'UAT Test Role' (delete/deactivate after) | Role appears in the list; audit entry recorded
ADMIN-ROL-03 | Edit role | Assign permissions | 1. Open a role 2. Toggle several permissions on/off 3. Save 4. Reopen |  | Saved toggles persist; member count unchanged
ADMIN-ROL-04 | Permission matrix | Matrix view | 1. Open Permissions 2. Locate a role column and toggle a cell 3. Save |  | Matrix shows roles x permissions; toggle animates; change persists after reload
ADMIN-ROL-05 | Permissions | Effect on user | 1. Remove a permission from a role 2. Login as a user with ONLY that role |  | Corresponding function is hidden/refused for that user (restore afterwards)

## Organisation
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ADMIN-ORG-01 | Hierarchy | Tree renders | 1. Open Org Hierarchy |  | Organisation tree shows with expand/collapse; correct parent-child structure
ADMIN-ORG-02 | Hierarchy | Add unit | 1. Add a child org unit (EN + AR names) 2. Save |  | New unit appears under its parent; available in user org dropdown
ADMIN-ORG-03 | Hierarchy | Edit / deactivate unit | 1. Rename a test unit 2. Deactivate it |  | Rename persists; deactivated unit flagged and not offered for new users

## System Administration
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ADMIN-SYS-01 | Module registry | List + toggle | 1. Open Module Registry 2. Toggle a non-critical module inactive and back |  | Modules (PC/DT/HR/FL/CC...) listed with status; toggle persists
ADMIN-SYS-02 | Approval templates | View / edit template | 1. Open Approval Templates 2. Open one template and review steps (sequence, role, escalation days) 3. Edit a non-production template |  | Steps listed in order; edits persist
ADMIN-SYS-03 | Approval monitor | In-flight instances | 1. Open Approval Monitor 2. Filter by module/status |  | Live approval instances with current step; filters work
ADMIN-SYS-04 | Lookups | Add lookup value | 1. Open Lookups 2. Pick a category (e.g. a status set) 3. Add a value (code + EN/AR names) 4. Edit it, then disable it | Category CC_REPLACEMENT_REASON — add code UAT_TEST | Value appears immediately; edits persist; disabled value stops appearing in module dropdowns
ADMIN-SYS-05 | System settings | Edit a setting | 1. Open System Settings 2. Edit a non-system setting value 3. Save and refresh |  | New value persists; system-flagged settings are read-only
ADMIN-SYS-06 | System settings | Secrets masked | 1. Locate a key/password-type setting (e.g. API key) |  | Value displays as ******** ; saving the mask back is refused (no secret overwrite)
ADMIN-SYS-07 | Theme setting | Brand color from settings | 1. Edit THEME_BRAND_COLOR (e.g. #7B1FA2) 2. Hard-refresh the app | THEME_BRAND_COLOR = #7B1FA2 (restore #C74634 after) | App chrome (buttons, accents) adopts the new color; restore the original afterwards
ADMIN-SYS-08 | Audit log | Pagination + filter | 1. Open Audit Log 2. Check pager caption 3. Filter by action (e.g. LOGIN) 4. Page through |  | Server-paged list; filter narrows rows; newest entries first; your own recent actions appear
ADMIN-SYS-09 | Appearance | Theme switch | 1. Open Appearance 2. Switch theme and back |  | Theme applies immediately and persists across refresh

## Delegations & Announcements
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ADMIN-DLG-01 | My delegations | Profile shows real data | 1. Open My Workspace > My Profile 2. Scroll to My Delegations | Login AYESHA.AMERI — shows 'Acting for Naser Al Khaja' (incoming, seeded) | Real delegations from the server (not placeholders); outgoing show 'Delegating to', incoming show 'Acting for'
ADMIN-DLG-02 | Create delegation | Delegate my authority | 1. In My Profile click + New Delegation 2. Pick a user, end date (e.g. +7 days), reason 3. Create | Delegate to HASHEM.ALKABBI, end date +7 days, reason 'UAT' | Delegation appears ACTIVE in the list; the delegate now sees your pending approvals with an 'acting for' badge
ADMIN-DLG-03 | Acting for | Delegate sees the queue | 1. Login as the delegate 2. Open Pending Approvals (Admin) or the module's approvals page | Login AYESHA.AMERI — NASER's pending items carry 'acting for' badge | Items requiring the delegator's role are listed with an 'acting for <name>' badge; delegate can approve/reject
ADMIN-DLG-04 | Cancel delegation | Stop the cover | 1. As the delegator (or SYS_ADMIN) cancel the ACTIVE delegation | Cancel the delegation created in the previous case | Status becomes CANCELLED; the delegate's queue no longer shows the delegated items
ADMIN-DLG-05 | Oversight | System > Delegations | 1. Login as SYS_ADMIN 2. Open System > Delegations 3. Filter by status | Seeded NASER→AYESHA row + your test rows | All delegations platform-wide with delegator, delegate, scope, window; expired ones flip to EXPIRED automatically
ADMIN-DLG-06 | Announcements admin | Create an announcement | 1. Open System > Announcements 2. + New Announcement: EN+AR titles, severity, audience 3. Save | Title 'UAT banner test' / INFO / Everyone (deactivate after) | Announcement listed; appears as a colored banner at the top of the targeted apps within a refresh
ADMIN-DLG-07 | Banner audience | Module-targeted banner | 1. Create a WARNING announcement targeted at module CREDIT_CARDS 2. Open the CC app, then the PC app | WARNING targeted at module CREDIT_CARDS (seeded example exists) | Banner shows in CC only; PC does not show it; ALL announcements show everywhere
ADMIN-DLG-08 | Banner dismiss | Dismiss persists for the session | 1. Click the X on a banner 2. Navigate around 3. Close the tab, reopen and login | Seeded banner: 'Freelancers & Credit Cards modules are live' | Dismissed banner stays hidden while the session lasts; reappears in a new session if still active
ADMIN-DLG-09 | Deactivate | Pull an announcement | 1. In System > Announcements deactivate one | Deactivate your 'UAT banner test' announcement | It stops appearing in all apps (after refresh); stays in the admin list as inactive

## Shell & Platform
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ADMIN-SHL-01 | Module switcher | Switch to another module | 1. Click the module dropdown in the top bar 2. Choose HR (or PC/DT) |  | Target app opens WITHOUT a second login (shared session); switcher highlights the current module
ADMIN-SHL-02 | Module switcher | FL + CC are live | 1. Open the module dropdown | Switcher: Freelancers APP 203 + Credit Cards APP 202 (no 'soon') | Freelancers (APP 203) and Credit Cards (APP 202) appear WITHOUT a 'soon' badge and open their apps
ADMIN-SHL-03 | Language | EN to AR live switch | 1. Click the ع button in the top bar |  | Entire page flips RTL instantly: top bar, side nav, content; Arabic font; numbers stay Latin digits
ADMIN-SHL-04 | Language | AR persists across login | 1. Switch to AR 2. Logout, close browser, reopen and login |  | App opens in Arabic (server-stored preference); switch back to EN at the end
ADMIN-SHL-05 | Side navigation | Collapse / expand | 1. Click the hamburger icon |  | Side nav collapses/expands; content area adjusts
ADMIN-SHL-06 | Role-based nav | Menu matches role | 1. Login as a non-admin user |  | Admin-only groups (User Management, System) are hidden
ADMIN-SHL-07 | Error handling | API failure feedback | 1. Disconnect network (or stop the proxy) 2. Try loading a list |  | Friendly error state with Retry + a toast; no frozen skeleton, no blank screen

## Wave Enhancements
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ADMIN-WAV-01 | Bootstrap | One-call /boot on login | 1. Open DevTools > Network 2. Login |  | A single GET /dct/boot fires right after login (instead of separate settings/prefs/unread calls); brand color and language apply immediately
ADMIN-WAV-02 | Landing page | Role-based landing route | 1. As admin set system setting LANDING_MANAGER = profile 2. Login as a MANAGER user (e.g. NASER.ALKHAJA) 3. Restore LANDING_MANAGER = dashboard afterwards |  | The manager lands on My Profile after login instead of the dashboard (when /boot answers within the 800ms cap; otherwise dashboard)
ADMIN-WAV-03 | Command palette | Ctrl+K opens + navigates | 1. Press Ctrl+K anywhere 2. Type 'role' 3. Choose 'Roles' with arrow keys + Enter |  | Vault-styled palette opens; Navigation group lists matching pages; Enter navigates to Roles and closes the palette
ADMIN-WAV-04 | Command palette | Search users | 1. Press Ctrl+K 2. Type at least 2 letters of a username (e.g. AYESHA) 3. Pick the user result |  | Users group shows matching users; selecting one opens that user's edit page
ADMIN-WAV-05 | Feature flags | Kill switch disables palette | 1. System Settings: set FEATURE_COMMAND_PALETTE = N 2. Reload the app and press Ctrl+K 3. Restore Y afterwards |  | With the flag off, Ctrl+K does nothing (no palette); after restoring Y + reload it works again
ADMIN-WAV-06 | Undo toast | Deactivate user + Undo | 1. Users: click the deactivate (trash) icon on a test user 2. Click Undo in the toast within 8 seconds |  | User flips to Inactive immediately with a '<name> deactivated' toast carrying an Undo action; Undo restores Active and shows a reactivated toast
ADMIN-WAV-07 | Bulk actions | Bulk deactivate | 1. Users: tick the checkboxes of two test users 2. In the bulk bar click Deactivate, then Apply in the confirm dialog |  | Bulk bar shows '2 selected'; after Apply a 'Applied to 2 user(s)' toast appears and both rows show Inactive
ADMIN-WAV-08 | Bulk actions | Bulk activate restores | 1. Select the same two users 2. Bulk bar > Activate > Apply |  | Both rows show Active again
ADMIN-WAV-09 | Bulk actions | Bulk assign role | 1. Select one test user 2. Bulk bar > Assign role… > choose a role > Apply |  | Role appears in the user's Roles badges after the list reloads
ADMIN-WAV-10 | Form guard | Unsaved changes warning | 1. Edit a user; change Display Name without saving 2. Click Users in the side nav 3. Cancel the dialog, then try again and accept |  | Browser confirm 'unsaved changes' appears; Cancel stays on the edit page; OK leaves without saving
ADMIN-WAV-11 | Idle warning | Still-there dialog | 1. Stay fully idle (no mouse/keyboard) until SESSION_TIMEOUT_MINS minus 5 minutes elapse (testers: temporarily lower the timeout) 2. Click 'Stay signed in' |  | A 'Still there?' dialog appears before the session dies; Extend keeps the session alive and closes the dialog
ADMIN-WAV-12 | Template lifecycle | Clone live template as draft | 1. System > Approval Templates 2. Search UAT_WAVE_FLOW 3. Click the clone icon on the ACTIVE row |  | Toast 'Draft created…'; a new row UAT_WAVE_FLOW~D with a Draft badge appears; live row unchanged
ADMIN-WAV-13 | Template lifecycle | Edit draft steps | 1. Open the draft (pencil icon) 2. Rename step 1 and move it down 3. Save, reopen |  | Steps are editable only on drafts; rename + reorder persist after reopening
ADMIN-WAV-14 | Template lifecycle | Activate draft | 1. Click Activate on the draft row 2. Confirm |  | Toast 'Draft activated — previous version archived'; draft becomes the ACTIVE UAT_WAVE_FLOW (version +1); old row archived as UAT_WAVE_FLOW~V1
ADMIN-WAV-15 | Audit log | Before/after diff row | 1. System > Audit Log 2. Click any row |  | Row expands with a lazy-loaded panel: either a Field/Before/After diff table or the message that no snapshot was recorded
ADMIN-WAV-16 | Audit log | Export CSV | 1. Audit Log > Export CSV |  | A .csv file downloads containing the filtered audit entries
ADMIN-WAV-17 | Dashboard | Customize layout persists | 1. Dashboard > Customize 2. Hide one stat card, click Done 3. Reload the app |  | Hidden card stays hidden after reload (preference saved per user); Customize > re-enable restores it
ADMIN-WAV-18 | Notifications | Unread badge count endpoint | 1. Note the bell badge number 2. Compare with GET /dct/notifications/count |  | Badge equals the endpoint's count; badge refreshes within ~60s of new notifications without a reload
ADMIN-WAV-19 | Audit info | Created/Updated meta on edit pages | 1. Open any existing user in Edit 2. Scroll to the bottom |  | An audit line shows Created by/at and Updated by/at when available

## Enhancement Round 2
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ADMIN-ENH-01 | Feature flags | FEATURES render as toggles | 1. System Settings > FEATURES card 2. Flip a switch (e.g. FEATURE_IDLE_WARNING) and Save 3. Verify, then flip it back and Save |  | FEATURE_* rows render as on/off switches (not text boxes); the flip persists and the feature honours it after reload
ADMIN-ENH-02 | Landing page | Role edit landing dropdown | 1. Edit a role (e.g. MANAGER) 2. Pick a Landing page from the dropdown and Save 3. Restore Default afterwards |  | Saving writes the LANDING_<ROLE> system setting; users with that role land on the chosen page at next login
ADMIN-ENH-03 | Audit log | Date-range filter | 1. Audit Log: set From and To to today 2. Set From to a future date |  | Today's range shows entries (server-filtered count in the pager); a future From date shows an empty list
ADMIN-ENH-04 | Audit log | Server-side CSV export | 1. Audit Log > Export CSV |  | The CSV is built by the server over the FULL filtered history (up to 20k rows) — not capped at the first 1000 rows
ADMIN-ENH-05 | Sessions | Active sessions page | 1. System > Active Sessions |  | All sessions inside the inactivity window are listed with masked ids (…last6), login/last-activity times and IP; your own row is badged 'this device'
ADMIN-ENH-06 | Sessions | Revoke signs the user out | 1. Login as a test user in another browser 2. In Active Sessions click Revoke on that user and confirm |  | All of that user's sessions close; their next click/navigation bounces them to the login page
ADMIN-ENH-07 | Bulk actions | Bulk remove role | 1. Users: select a test user 2. Bulk bar > Remove role… > pick the role > Apply |  | The role disappears from the user's badges; other roles are untouched
ADMIN-ENH-08 | Bulk actions | Bulk set organisation | 1. Select a test user 2. Bulk bar > Set organisation… > pick an org > Apply |  | The Organisation column updates for the selected user(s)
ADMIN-ENH-09 | Command palette | Action verbs | 1. Ctrl+K 2. Type 'create user' and pick the action |  | An Actions group offers Create user / Create role / New announcement / New delegation; Create user opens a blank Add User form
ADMIN-ENH-10 | Command palette | Recent pages | 1. Visit Users, then Roles, then Home 2. Press Ctrl+K with an empty query |  | A Recent group lists the pages just visited; picking one navigates back to it
ADMIN-ENH-11 | Template history | Version history + step diff | 1. Approval Templates: search UAT_WAVE_FLOW 2. Click the history (🕘) icon on the ACTIVE row |  | Archived ~V versions no longer clutter the main list; the History modal shows live + archived versions with step-diff chips (added/removed/reordered vs live)
ADMIN-ENH-12 | Template history | Restore archived version | 1. In the History modal click Restore on an archived version 2. Confirm |  | A new ~D draft is created with the archived steps; the live template is unchanged until the draft is activated
ADMIN-ENH-13 | Module rollout | Palette + idle warning in module apps | 1. Open Petty Cash (or DT/HR/FL/CC) via the switcher 2. Press Ctrl+K 3. Stay idle to see the warning (testers: lower the timeout) |  | The command palette opens with that app's navigation; the idle 'Still there?' warning and unsaved-changes guard are active in all module apps