## Instructions
i-Finance UAT Script
Credit Cards (App 202) — Cards, Requests, Replenishments
Environment URL | (fill in: e.g. http://localhost:8080 or the deployed URL)
Build / version date | 2026-06-12 (Phase 4)
UAT round
Lead tester
Start date
End date
How to test
1. Each tab is one functional area. Work top-to-bottom; one row = one test case.
2. Follow the Steps column exactly; compare the outcome with Expected Result.
2b. Sample Data / Records tells you WHICH seeded record, account or value to use — prefer it over inventing your own so results are reproducible.
3. Set Status from the dropdown: Pass / Fail / Blocked / N/A.
4. On Fail or Blocked, ALWAYS fill Comments (what happened, screenshots reference, error text).
5. Fill Tested By + Test Date on every executed row.
6. Login accounts: use the quick-login buttons on the login page, or accounts provided by the admin. Never write passwords in this file.
7. Hard-refresh (Ctrl+F5) after the team deploys a fix before retesting.
Status legend
Pass | Works exactly as the Expected Result describes
Fail | Does not match the Expected Result (describe in Comments)
Blocked | Cannot be executed (missing data/role/dependency failed)
N/A | Not applicable to this round/role
Seeded UAT data (your starting point)
- CC roles: NASER.ALKHAJA = CC_ADMIN; card holders: SHAIKHA.ALSUWAIDI (CC-2026-00002, 20k) and HASHEM.ALKABBI (CC-2026-00003, 12k). CC-2026-00001 is a CLOSED test card.
- CCM-2026-05-00001 (May statement, 3 merchant lines, 1,970.50) - SUBMITTED, awaiting approval.
- One INCREASE_LIMIT request exists in WITHDRAWN state (negative-path evidence).
- Doc requirements seeded: 4 mandatory documents for NEW_CARD; check the wizard checklist against them.
Live summary
Functional area | Cases | Pass | Fail | Blocked | Executed %
Access & Session | 3
Dashboard | 2
My Card | 4
Card Requests | 6
Replenishments | 5
Approvals | 3
Administration | 4
Shell & Language | 2
TOTAL

## Access & Session
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
CC-ACC-01 | Shared session | Entry from Admin | 1. Login in Admin 2. Switch to Credit Cards via the module dropdown | Holders: SHAIKHA.ALSUWAIDI (CC-2026-00002), HASHEM.ALKABBI (CC-2026-00003) · CC_ADMIN = NASER.ALKHAJA | CC opens logged-in; holder vs approver vs CC_ADMIN nav per role
CC-ACC-02 | No session | Direct open without login | 1. Fresh private window > CC URL | Holders: SHAIKHA.ALSUWAIDI (CC-2026-00002), HASHEM.ALKABBI (CC-2026-00003) · CC_ADMIN = NASER.ALKHAJA | Redirected to Admin login
CC-ACC-03 | Role gating | Admin menus | 1. Compare menus as a holder (SHAIKHA.ALSUWAIDI) vs CC_ADMIN (NASER) | Holders: SHAIKHA.ALSUWAIDI (CC-2026-00002), HASHEM.ALKABBI (CC-2026-00003) · CC_ADMIN = NASER.ALKHAJA | All Cards / Proxies / Module Settings only for CC_ADMIN/SYS_ADMIN; Approvals for MANAGER+

## Dashboard
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
CC-DSH-01 | Stats | Cards show live numbers | 1. Open CC Dashboard |  | Active cards, total credit limit, pending requests, replenishments due — sensible values
CC-DSH-02 | Charts | Limits + compliance | 1. Wait for both charts |  | Credit limits by organisation bar + 6-month replenishment compliance (submitted vs due) render

## My Card
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
CC-CRD-01 | Card visual | My card renders | 1. Login as a card holder 2. Open My Card | Login SHAIKHA.ALSUWAIDI — CC-2026-00002 (20,000 AED) | Card visual with number, holder, limit, expiry; status badge; greyed if not ACTIVE
CC-CRD-02 | Limit history | Timeline | 1. Check the Limit History table | CC-2026-00002 — INITIAL 0→20,000 row from registration | INITIAL row from registration; INCREASE/DECREASE rows after approved limit changes
CC-CRD-03 | Due banner | Replenishment due | 1. As a holder whose current-month statement is missing open My Card | SHAIKHA.ALSUWAIDI — May submitted, current month missing → banner shows | Amber 'this month's replenishment has not been submitted' banner with a shortcut button
CC-CRD-04 | No card | Holder without card | 1. Login as a user with no card 2. Open My Card | Login SHAIKHA.GALAMERI (no card) | Friendly empty state offering a New Card request (no errors)

## Card Requests
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
CC-REQ-01 | Wizard | Type tiles | 1. Open Card Requests > + New Request |  | 5 tiles: New Card / Increase / Decrease / Replacement / Close; 3-step wizard with progress
CC-REQ-02 | New card | Full happy path | 1. Pick New Card, enter limit + reason 2. Save Draft & Continue 3. Upload every mandatory document 4. Submit | Limit 10,000 · 4 mandatory NEW_CARD docs (any small PNG/PDF) | Submit only enabled once all mandatory docs are uploaded; request goes to approval
CC-REQ-03 | Doc checklist | Mandatory docs enforced | 1. In step 3 leave a mandatory document missing 2. Try Submit | Leave 'Salary Certificate' (or any mandatory doc) missing | Submit disabled / blocked with a clear message naming the missing document
CC-REQ-04 | Increase limit | Validation | 1. Create INCREASE_LIMIT with a limit LOWER than the current one 2. Submit | CC-2026-00002 (current 20,000) — request 15,000 to test the block | Blocked: requested limit must exceed the current limit
CC-REQ-05 | Withdraw | Pull back a submitted request | 1. Open your SUBMITTED request 2. Withdraw | Create INCREASE_LIMIT 25,000 on CC-2026-00003, submit, then withdraw (a seeded WITHDRAWN example exists) | Status WITHDRAWN; leaves the approver queue; card free for new requests
CC-REQ-06 | Detail | Request detail | 1. Open a request |  | Type, card, limits, reason, documents and audit info all shown

## Replenishments
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
CC-RPL-01 | Create | New monthly statement | 1. Open Replenishments > + New Replenishment 2. Pick your card + last month 3. Create Draft | CC-2026-00002 + May 2026 → duplicate blocked; use the current month | Draft CCM-YYYY-MM-NNNNN created; one statement per card per month enforced
CC-RPL-02 | Lines | Merchant lines editor | 1. In the detail add 3 lines: date, merchant, amount, GL or Project coding, receipt flag 2. Save Lines | Lines: Etisalat 420.50 / Amazon AE 1,310.00 / ADNOC 240.00 (as in CCM-2026-05-00001) | Lines saved; running total recalculates; receipt counter updates
CC-RPL-03 | Validation | Line rules | 1. Try saving a line without merchant/amount/date or GL code |  | Clear per-line validation; nothing saved
CC-RPL-04 | Submit | Send for approval | 1. Submit the statement | Your current-month draft from the previous cases | Status SUBMITTED; appears in the approvals queue; only the holder or an active proxy may submit
CC-RPL-05 | Proxy | Proxy submits for the holder | 1. As CC_ADMIN create a proxy for a card 2. Login as the proxy and create/submit a statement for that card | Proxy HASHEM.ALKABBI on CC-2026-00002 (create in Proxies first) | Proxy can submit; non-proxies are blocked with a clear message

## Approvals
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
CC-APR-01 | Queue | Pending list | 1. Login as an approver (MANAGER/CC_ADMIN) 2. Open Pending Approvals | CCM-2026-05-00001 (May statement, 1,970.50) — SUBMITTED, in the approver queue | CC requests + replenishments awaiting your step; badge matches
CC-APR-02 | Comment required | Approve needs a comment | 1. Approve with an empty comment | CCM-2026-05-00001 (May statement, 1,970.50) — SUBMITTED, in the approver queue | Blocked; succeeds with a comment
CC-APR-03 | Lifecycle | Approved request applies | 1. Fully approve an INCREASE_LIMIT request | INCREASE_LIMIT on CC-2026-00003: 12,000 → 14,000 | Card limit updates; INCREASE row added to limit history; holder notified

## Administration
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
CC-ADM-01 | All cards | Registry + search | 1. As CC_ADMIN open All Cards 2. Search and filter by status | CC-2026-00001 (CLOSED) · 00002 (SHAIKHA.ALSUWAIDI) · 00003 (HASHEM) | All cards org-wide; pending operation chips for in-flight requests
CC-ADM-02 | Register card | From approved NEW_CARD | 1. + Register Card 2. Pick an APPROVED NEW_CARD request 3. Fill holder, mother name, nationality, limit, expiry, email, org 4. Register | Approve a fresh NEW_CARD request first (wizard case), then register it here | Card created ACTIVE with CC-YYYY-NNNNN number + INITIAL limit history; holder notified
CC-ADM-03 | Proxies | Manage proxies | 1. Open Proxies 2. Create one (card + proxy user + window) 3. Deactivate it | Card CC-2026-00002 · proxy SHAIKHA.GALAMERI · window today → +30 days | Proxy listed; deactivation removes submit rights
CC-ADM-04 | Module settings | CC settings | 1. Open Module Settings 2. Edit a value (e.g. REPLENISHMENT_DUE_DAY) 3. Save + refresh | REPLENISHMENT_DUE_DAY (restore the value after) | Persists; non-admins do not see the page

## Shell & Language
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
CC-SHL-01 | Switcher | Cross-module hop | 1. Module dropdown > Admin / FL and back |  | No re-login; CC shows live (no 'soon' badge)
CC-SHL-02 | Arabic | RTL pass | 1. Switch to AR 2. Walk Dashboard + My Card + a request detail |  | Mirrored layout, Arabic labels, Latin digits; card visual unaffected