## Instructions
i-Finance UAT Script
Freelancers (App 203) — Registrations, Contracts, Payments
Environment URL | (fill in: e.g. http://localhost:8080 or the deployed URL)
Build / version date | 2026-06-12 (Phase 4)
UAT round
Lead tester
Start date
End date
How to test
1. Each tab is one functional area. Work top-to-bottom; one row = one test case.
2. Follow the Steps column exactly; compare the outcome with Expected Result.
2b. Sample Data / Records tells you WHICH seeded record, account or value to use — prefer it over inventing your own so results are reproducible.
3. Set Status from the dropdown: Pass / Fail / Blocked / N/A.
4. On Fail or Blocked, ALWAYS fill Comments (what happened, screenshots reference, error text).
5. Fill Tested By + Test Date on every executed row.
6. Login accounts: use the quick-login buttons on the login page, or accounts provided by the admin. Never write passwords in this file.
7. Hard-refresh (Ctrl+F5) after the team deploys a fix before retesting.
Status legend
Pass | Works exactly as the Expected Result describes
Fail | Does not match the Expected Result (describe in Comments)
Blocked | Cannot be executed (missing data/role/dependency failed)
N/A | Not applicable to this round/role
Seeded UAT data (your starting point)
- FL roles: AYESHA.AMERI = FL_ADMIN, NASER.ALKHAJA = FL_MANAGER, SHAIKHA.GALAMERI = FL_USER.
- Layla Hassan (FL-VND-000001) - ACTIVE freelancer with bank account, documents and contract FL-CON-000001 (24k, ACTIVE, 1 voucher PAID): use for detail/schedule/voucher tests.
- FL-CON-000002 (84k) - pending at the FL_ADMIN step: use for the >=50k two-step approval test.
- FL-REG-000004 (Omar Saleh) - DRAFT; FL-REG-000005 (Mariam Khalil) - SUBMITTED, in the manager queue.
- One amendment, one deliverable, one renewal and near-expiry documents exist from the lifecycle seed.
Live summary
Functional area | Cases | Pass | Fail | Blocked | Executed %
Access & Session | 3
Dashboard | 2
Registrations | 5
Freelancers | 5
Contracts | 7
Payments | 5
Compliance | 2
Approvals | 3
Administration | 1
Shell & Language | 2
Enhancements | 5
TOTAL

## Access & Session
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
FL-ACC-01 | Shared session | Entry from Admin | 1. Login in Admin 2. Switch to Freelancers via the module dropdown | FL_USER = SHAIKHA.GALAMERI · FL_MANAGER = NASER.ALKHAJA · FL_ADMIN = AYESHA.AMERI | FL opens logged-in; viewer/manager/admin nav per role (FL_USER / FL_MANAGER / FL_ADMIN)
FL-ACC-02 | No session | Direct open without login | 1. Fresh private window > FL URL | FL_USER = SHAIKHA.GALAMERI · FL_MANAGER = NASER.ALKHAJA · FL_ADMIN = AYESHA.AMERI | Redirected to Admin login
FL-ACC-03 | Role gating | Compliance/Approvals/Admin menus | 1. Compare menus as FL_USER (SHAIKHA.GALAMERI) vs FL_MANAGER (NASER) vs FL_ADMIN (AYESHA) | FL_USER = SHAIKHA.GALAMERI · FL_MANAGER = NASER.ALKHAJA · FL_ADMIN = AYESHA.AMERI | Compliance + Approvals groups appear for managers+; Module Settings only for FL_ADMIN/SYS_ADMIN

## Dashboard
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
FL-DSH-01 | Stats | Cards show live numbers | 1. Open FL Dashboard |  | Active freelancers, active contracts (+AED total), vouchers awaiting approval, documents expiring — all sensible values
FL-DSH-02 | Charts | Spend + expiry horizon | 1. Wait for both charts |  | Committed-vs-Paid by organisation bar chart + document expiry horizon chart render with data

## Registrations
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
FL-REG-01 | List | Paged list + search | 1. Open Registrations 2. Search by name 3. Filter by status | FL-REG-000004 (Omar Saleh, DRAFT) · FL-REG-000005 (Mariam Khalil, SUBMITTED) | Server-paged list; filters work; FL-REG numbers shown
FL-REG-02 | Create | New registration draft | 1. + New Registration: names, date of birth, nationality, email, mobile, specialization 2. Save | Name 'Test Freelancer UAT' · nationality from dropdown · test.fl.uat@example.com | Draft saved with FL-REG-NNNNNN number; appears in the list as DRAFT
FL-REG-03 | Photo | Photo required to submit | 1. Open a DRAFT registration without a photo 2. Try Submit 3. Upload a photo and submit again | FL-REG-000004 (no photo yet) · any JPG/PNG | Submit blocked until a photo is uploaded; with photo it submits
FL-REG-04 | Submit | Send for approval | 1. Submit a complete draft | Your draft from the previous case (photo uploaded) | Status SUBMITTED; appears in the FL manager's approvals queue
FL-REG-05 | Approve | Approval creates the freelancer | 1. As FL_MANAGER approve the registration (then FL_ADMIN if a second step shows) | FL-REG-000005 — in NASER.ALKHAJA's queue | On final approval a freelancer profile is created automatically with a FL-VND vendor number

## Freelancers
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
FL-VND-01 | List | Directory | 1. Open Freelancers | Layla Hassan — FL-VND-000001 (ACTIVE) | Active freelancers with vendor number, name, specialization, status
FL-VND-02 | Detail | Tabs | 1. Open a freelancer | FL-VND-000001 (has bank account, contract, documents) | Profile / Bank Accounts / Contracts / Documents tabs all load; audit info shows created/updated in local time
FL-VND-03 | Bank | Add bank account | 1. In Bank Accounts add IBAN/bank details 2. Save | IBAN AE07 0331 2345 6789 0123 456 · any seeded bank | Account listed; primary flag honoured
FL-VND-04 | Status | Change status | 1. Use Change Status (e.g. ACTIVE > INACTIVE and back) |  | Status updates with a reason; reflected in the list
FL-VND-05 | Documents | Add document with expiry | 1. In Documents add a document with a near-future expiry 2. Upload the file | Expiry +20 days (so it appears in Compliance) | Document saved; appears in Compliance > Documents with days-to-expiry

## Contracts
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
FL-CON-01 | List | Contracts with billing bar | 1. Open Contracts | FL-CON-000001 (24k ACTIVE, ~17% billed) · FL-CON-000002 (84k, pending) | Contracts with totals, status and % billed progress bar
FL-CON-02 | Create | New contract draft | 1. + New Contract: freelancer, title, dates, total amount, billing method, GL or Project coding 2. Save | FL-VND-000001 · 12 months · GL coding from dropdown | Draft saved with FL-CON number; GL/PROJECT coding toggle works
FL-CON-03 | Submit small | < 50k = 1 approval step | 1. Submit a contract under AED 50,000 2. Approve as FL_MANAGER | Amount 24,000 — approve as NASER.ALKHAJA only | Contract becomes ACTIVE after ONE approval; payment schedule generated automatically
FL-CON-04 | Submit large | >= 50k = 2 approval steps | 1. Submit a contract of AED 50,000+ (seeded: FL-CON-000002, 84k) 2. Approve as FL_MANAGER | FL-CON-000002 (84k) — already at step 2; approve as AYESHA.AMERI (FL_ADMIN) | After step 1 it is still pending at the FL_ADMIN step; only after step 2 does it activate
FL-CON-05 | Detail | Schedule + tabs | 1. Open an ACTIVE contract | FL-CON-000001 — 6 monthly rows, June PAID | Payment Schedule / Amendments / Renewals / Details tabs; schedule rows match the billing method
FL-CON-06 | Amendment | Amend amount/end date | 1. + Amendment on an ACTIVE contract 2. Submit and approve it | FL-CON-000001 — one amendment already exists as reference | On approval the contract values update, version +1, schedule rebuilt
FL-CON-07 | Renewal | Renew a contract | 1. Renew from the contract detail 2. Submit and approve |  | A new contract version/row is created per the renewal terms

## Payments
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
FL-PAY-01 | Schedule | Due worklist | 1. Open Payment Schedule | FL-CON-000001 schedule — July onwards PENDING | Due/pending schedule rows across contracts with Generate Voucher actions
FL-PAY-02 | Voucher | Generate from schedule | 1. Click Generate Voucher on a due row | July 2026 row of FL-CON-000001 | Voucher FL-VCH created in DRAFT linked to the schedule row
FL-PAY-03 | Voucher | Invoice + submit | 1. Open the voucher detail 2. Enter invoice reference 3. Submit and approve | Invoice ref INV-UAT-001 | Voucher APPROVED; schedule row marked voucher-generated
FL-PAY-04 | Mark paid | FL_ADMIN settles | 1. As FL_ADMIN use Mark Paid on an approved voucher | Login AYESHA.AMERI — FL-VCH-000001 is the PAID reference | Payment status PAID; contract paid-total and % billed update
FL-PAY-05 | Deliverables | Accept / reject | 1. Open Deliverables 2. Accept one and reject another with a reason |  | States update; reason stored

## Compliance
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
FL-CMP-01 | Documents | Expiry filter + badge | 1. Open Compliance > Documents 2. Use the expiry filter (Expired / Expiring Soon / Valid) | Seeded near-expiry document on FL-VND-000001 | Filtered list with days-to-expiry; side-nav badge matches the expiring count
FL-CMP-02 | Navigate | Document to freelancer | 1. Click a document row |  | Opens the owning freelancer's Documents tab

## Approvals
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
FL-APR-01 | Queue | Pending list | 1. Login as FL_MANAGER (NASER) 2. Open Pending Approvals | Login NASER.ALKHAJA; pending: FL-REG-000005 (registration) + FL-CON-000002 (84k contract, step 2) | FL registrations/contracts/vouchers awaiting YOUR step; badge count matches
FL-APR-02 | Comment required | Approve needs a comment | 1. Click Approve and try to confirm with an empty comment | Login NASER.ALKHAJA; pending: FL-REG-000005 (registration) + FL-CON-000002 (84k contract, step 2) | Blocked with 'a comment is required'; with a comment it succeeds
FL-APR-03 | Reject / Return | Negative paths | 1. Reject one item; Return another (with comments) | Login NASER.ALKHAJA; pending: FL-REG-000005 (registration) + FL-CON-000002 (84k contract, step 2) | Statuses update; requester notified; returned item editable again

## Administration
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
FL-ADM-01 | Module settings | FL settings | 1. As FL_ADMIN open Module Settings 2. Edit a value (e.g. DOC_EXPIRY_ALERT_DAYS) 3. Save + refresh | DOC_EXPIRY_ALERT_DAYS (restore the value after) | Persists; non-admins do not see the page

## Shell & Language
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
FL-SHL-01 | Switcher | Cross-module hop | 1. Module dropdown > Admin / CC and back |  | No re-login; FL shows live (no 'soon' badge)
FL-SHL-02 | Arabic | RTL pass | 1. Switch to AR 2. Walk Dashboard + Registrations + a contract detail |  | Mirrored layout, Arabic labels, Latin digits; charts re-render

## Enhancements
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
FL-ENH-01 | Compliance deep link | Doc row opens Documents tab | 1. Open Compliance > Documents 2. Click a document row |  | Freelancer detail opens directly on the Documents tab (not Profile) — FL-CMP-02 fix
FL-ENH-02 | Bulk kill switch | Bulk button respects setting | 1. With ALLOW_BULK_VOUCHER_GENERATION = N open Payment Schedule 2. Call POST /fl/schedule/bulk-generate directly |  | No 'Generate All Due' button on the page; direct API call refused with 403
FL-ENH-03 | Bulk generation | Generate all due vouchers | 1. Set ALLOW_BULK_VOUCHER_GENERATION = Y 2. Reload Payment Schedule 3. Generate All Due > Generate 4. Restore the setting to N |  | Button appears; one DRAFT voucher per PENDING row without an open voucher; rows flip to VOUCHER_GENERATED; toast shows the created count
FL-ENH-04 | Unsaved changes guard | Dirty form warns on navigation | 1. Open a contract/registration edit form 2. Change a field without saving 3. Click another nav item |  | Confirm dialog about unsaved changes; Cancel stays, OK leaves; after Save no warning
FL-ENH-05 | Command palette | Ctrl+K navigation | 1. Press Ctrl+K anywhere in FL 2. Type a page name and press Enter |  | Palette opens with FL navigation entries; Enter navigates to the page