## Instructions
i-Finance UAT Script
HR (App 205) — Employees, Structure, Compliance
Environment URL | (fill in: e.g. http://localhost:8080 or the deployed URL)
Build / version date | 2026-06-12 (Phase 4)
UAT round
Lead tester
Start date
End date
How to test
1. Each tab is one functional area. Work top-to-bottom; one row = one test case.
2. Follow the Steps column exactly; compare the outcome with Expected Result.
2b. Sample Data / Records tells you WHICH seeded record, account or value to use — prefer it over inventing your own so results are reproducible.
3. Set Status from the dropdown: Pass / Fail / Blocked / N/A.
4. On Fail or Blocked, ALWAYS fill Comments (what happened, screenshots reference, error text).
5. Fill Tested By + Test Date on every executed row.
6. Login accounts: use the quick-login buttons on the login page, or accounts provided by the admin. Never write passwords in this file.
7. Hard-refresh (Ctrl+F5) after the team deploys a fix before retesting.
Status legend
Pass | Works exactly as the Expected Result describes
Fail | Does not match the Expected Result (describe in Comments)
Blocked | Cannot be executed (missing data/role/dependency failed)
N/A | Not applicable to this round/role
Seeded UAT data (your starting point)
- 5 active employees incl. E1101 Mohammed Al Mansoori, E1102 Fatima Al Hosani, E1103 Omar Khalil (seeded).
- Documents seeded with expiries ~20 / ~45 days (compliance list + badge data) and one ~13 months out.
- HR roles: SHAIKHA.GALAMERI = HR_MANAGER, SHAIKHA.ALSUWAIDI = HR_VIEWER.
Live summary
Functional area | Cases | Pass | Fail | Blocked | Executed %
Access & Session | 2
Dashboard | 2
People | 8
Structure | 4
Compliance | 3
Administration | 2
Shell & Language | 3
TOTAL

## Access & Session
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
HR-ACC-01 | Shared session | Entry from Admin | 1. Login in Admin 2. Switch to HR via the module dropdown |  | HR opens logged-in; viewer/manager/admin nav per role
HR-ACC-02 | No session | Direct open without login | 1. Fresh private window > HR URL |  | Redirected to Admin login

## Dashboard
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
HR-DSH-01 | Stats | Headcount cards | 1. Open HR Dashboard |  | Cards (headcount, vacancies, expiring docs) show live values
HR-DSH-02 | Charts | Headcount + expiry horizon | 1. Wait for both charts |  | Approved vs filled headcount chart + document expiry horizon chart render

## People
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
HR-EMP-01 | Employees list | Paged list | 1. Open Employees 2. Page next/previous | Seeded employees: E1101 Mohammed Al Mansoori, E1102 Fatima Al Hosani, E1103 Omar Khalil | Employee cards/rows with photo or initials; paging works without losing filters
HR-EMP-02 | Employees list | Search + filters | 1. Search by name 2. Filter by organisation and grade | Seeded employees: E1101 Mohammed Al Mansoori, E1102 Fatima Al Hosani, E1103 Omar Khalil | Server-side filtering; combined filters work; clear restores
HR-EMP-03 | Employee detail | Full record | 1. Open an employee | E1101 Mohammed Al Mansoori | Personal, job (position/grade/org), contacts, documents tabs all populated
HR-EMP-04 | Create | New employee | 1. New Employee: number, names EN/AR, hire date, position, org, grade 2. Save | Number E9901 · hire date today · any position/org/grade | Employee created and findable; appears in headcount
HR-EMP-05 | Edit | Update employee | 1. Edit job title / phone / org 2. Save and reopen | Seeded employees: E1101 Mohammed Al Mansoori, E1102 Fatima Al Hosani, E1103 Omar Khalil | Changes persist
HR-EMP-06 | Photo | Upload employee photo | 1. In employee detail click photo/upload 2. Choose an image | E1102 Fatima Al Hosani · small JPG/PNG (< 20KB if large files fail) | Picker opens; photo saved and shown in list + detail (small file < 20KB if large files fail)
HR-EMP-07 | Documents | Add employee document | 1. Add a document (type, number, expiry date) to an employee 2. Upload the file | Seeded employees: E1101 Mohammed Al Mansoori, E1102 Fatima Al Hosani, E1103 Omar Khalil | Document listed with expiry; appears in compliance views
HR-EMP-08 | Org hierarchy | Org chart | 1. Open Org Hierarchy | Seeded employees: E1101 Mohammed Al Mansoori, E1102 Fatima Al Hosani, E1103 Omar Khalil | Tree/chart of org units with employees; expand/collapse works

## Structure
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
HR-STR-01 | Positions | CRUD | 1. Open Positions 2. Create a position (title, org, grade, headcount) 3. Edit it 4. Try assigning an employee to it |  | Position created/edited; assignable to employees; filled count updates
HR-STR-02 | Jobs | CRUD | 1. Open Jobs 2. Create/edit a job |  | Job persists; selectable on positions/employees
HR-STR-03 | Grades | List + edit | 1. Open Grades 2. Edit a grade label |  | Grades listed; edit persists; grade dropdowns reflect it
HR-STR-04 | Locations | CRUD | 1. Open Locations 2. Add/edit a location |  | Location persists; selectable on employees/positions

## Compliance
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
HR-CMP-01 | Expiring documents | Expiry list + badge | 1. Open Documents (compliance) 2. Compare the side-nav badge number with rows | Seeded documents expiring in ~20 and ~45 days | Documents expiring within the window listed with days-left; badge matches
HR-CMP-02 | Document detail | Navigate to employee | 1. Click an expiring document |  | Opens the owning employee's documents tab
HR-CMP-03 | Renewal | Update expiry | 1. Update a document's expiry to a future date |  | Item leaves the expiring list; badge decreases

## Administration
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
HR-ADM-01 | Lookups | HR lookup values | 1. Open Lookups 2. Add/edit a value in an HR category |  | Value persists and appears in the matching dropdowns
HR-ADM-02 | Module settings | HR settings | 1. Open Module Settings 2. Edit a value and refresh |  | Persists; no errors

## Shell & Language
Test ID | Function | Test Scenario | Steps | Sample Data / Records | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
HR-SHL-01 | Switcher | Cross-module hop | 1. Module dropdown > Admin and back |  | No re-login
HR-SHL-02 | Arabic | RTL pass | 1. Switch to AR 2. Walk Employees + Dashboard |  | Mirrored layout; Arabic shell; Arabic names display correctly; Latin digits
HR-SHL-03 | Notifications | HR notifications | 1. Check the bell after document-expiry alerts run |  | Expiry notifications visible and readable