## Approval Hierarchy
The Approval Hierarchy.
Approver Key
TPC Director | Khader | TPC01
Contracts & Cost Estimation Director | Jayagopalan | TPC02
ZNM Contracts Admin & Claims Sr. Manager | Audrey | TPC03 | for ZNM.
Acting Contracts Admin & Claims Sr. Manager | Jawad | TPC04 | for GAD
Technical Support Officer | Ruth | TPC05
Contracts & Cost Estimation Manager | Saliny | TPC06
PME Acting Director | Basel | PME01
Project Director / Sr. PM Assigned | From the Tab (Project Managers) | PME02
Technical Management Director | Amol | PME03
Sr. Document Controller | Ferdie | PME04
Project Manager Senior Specialist | Ghadeer | PME05
VAR Approval Hierarchy
Submission | PMC
Recommended | PME02
Endorsed by | CS Rep | optional End User (yes/no)
Endorsed by | CS Director
Reviewed by | PME03
Approved by | PME01
Forward / Return by | TPC04 | only for GAD
Reviewed by | TPC02 / TPC03
Verified by | TPC01
Notification | TPC05 & TPC06
BM Approval Hierarchy
Submission | PMC
Recommended | PME02
Forward / Return by | TPC04 | only for GAD
Reviewed by (1) | TPC02
Reviewed by (2) | TPC03 | only for ZNM
Approved by | TPC01
Notification | TPC05 & TPC06
PACOF Approval Hierarchy
Submission | TPC02
Reviewed by | PME02
Reviewed by | PME03
Approved by | PME01
Forward / Return by | TPC04
Reviewed by | TPC02 / TPC03
Verified by | TPC01
Notification | TPC05 & TPC06
amount upto 1 million | Khalifa Ahmed Al Marzooqi
1 - 5 million | Adnan Mohammed AlAwadhi
Above 5 million | Procurement Committee
Variation Order Hierarchy *
Submission | PMC
Approved by | PME02
Approved by | PME03
Approved by | PME01
Forward/Return by | TPC04
Approved by | TPC02 / TPC03
Approved by | TPC01
Notification | TPC05 & TPC06
Contractual Signatory | (Undersecretary / Chairman)
* For the draft stage, there need not be any approvals. Once PACOF is approved, the parties may approve the VO in the pdf attachments submitted by the PMC

## Project Managers
Project Number | DCT Project Name | PM Assigned (PM)
4512000001 | Qar Al Hosn (QAH) | Oliver Heim
4512000002 | Mezyad Desert Park (MDP) | René von Mullen
4512000006 | Al Ain Museum (AAM) | René von Mullen
4512000011 | Qasr Al Manhal (QAM) | Oliver Heim
4512000012 | Zayed National Museum (ZNM) | George Zervas
4512000014 | Guggenheim Abu Dhabi (GAD) | Basel AbuYousef
4512000016 | Al Murrabba Fort (AMF) | Hasabo Mohamed
4512000018 | Al Ain Palace Museum | Maitha
4512000020 | Sir Bani Yas Phase II – Visitor Centre | Romi Sebastian
4512000023 | Culture Park (Museum Parking) | Khaled Alhousaini
4512000024 | Manarat Al Saadiyat energy Centre | Chadi Alagha
4512000026 | Al Manhal Palace - Facade Retention | Oliver Heim
4512000032 | Bassam Freiha Exhibition Pavilion | Chadi Alagha
| Al Wathba Enhancements | Chadi Alagha
4512000029 | Youth Orchestra Abu Dhabi | Oliver Heim
| House of Performing Arts | Oliver Heim
| Sphere Abu Dhabi | Mahdi Samhouri
| Al Jahili Fort | René von Mullen
| Louver Abu Dhabi - Parking & Shades | Chadi Alagha
| Saadiyat Tunnel Security Upgrade | Khaled Alhousaini