## Slide 1
DEPARTMENT OF CULTURE AND TOURISM — ABU DHABI · FINANCE DEPARTMENT
iFinance Implementation Plan
Deployment on a dedicated Oracle OCI tenancy within the Core42 data centre — co-located with the ADERP Oracle Fusion instance and fully integrated with it in both directions.
Submitted to: Finance Director — for review & approval
Methodology: Agile delivery — two-week sprints
Document: Implementation Plan v1.2 · 8 July 2026 · Prepared by the Finance Systems Team

## Slide 2
Executive Summary — Recommendation
• Solution: the iFinance platform, deployed on a dedicated Oracle OCI tenancy provisioned within the Core42 data centre — the same facility hosting the ADERP Oracle Fusion instance.
• Investment: a fixed quotation of USD 100,000, received for the entire eight-module scope — General Ledger, Reporting, Service Pricing, Freelancers, Team Management, Petty Cash, Duty Travel and Employee Housing.
• Methodology: Agile delivery — two-week sprints, each concluding with user acceptance testing (UAT), training and go-live; Sprint 2 delivers Reporting & BI and Service Pricing together.
• Timeline: tenancy provisioned within one week of contract signature; the first module (General Ledger) live in week 3; a further module every two weeks; full scope live in ≈ 3 months.
• Rationale: the technology best aligned with ADGE and Oracle Fusion · full bidirectional Fusion integration · the fastest achievable delivery · the lowest total cost of the available options.
• Critical path: a single enabling action — procurement of the Oracle OCI tenancy within Core42.
iFinance Implementation Plan · DCT Finance Department · July 2026
2

## Slide 3
Key Figures
USD 100K
Fixed quotation — entire 8-module scope
8
Business modules delivered
≈ 3 mo
Full scope live, from contract signature
Week 3
First module live — General Ledger
~12.5K
Average cost per module (USD)
100%
Data resident in Abu Dhabi (Core42)
iFinance Implementation Plan · DCT Finance Department · July 2026
3

## Slide 4
1 Why This Option
TECHNOLOGY ALIGNMENT
Best technology — aligned with ADGE & Oracle Fusion
• End-to-end Oracle stack — OCI, Autonomous Database, APEX/ORDS, Oracle JET.
• Same technology family, and the same Core42 data centre, as ADERP Fusion.
• Conforms to ADGE cloud & data-residency direction — no new vendor.
FUSION INTEGRATION — BOTH DIRECTIONS
Fully integrated with Oracle Fusion
• Outbound: scheduled extracts of GL, budgets, projects, AP / PO / PR — already operational in pilot.
• Inbound: approved transactions (e.g. petty-cash reimbursements) post back to Fusion AP.
• Co-location keeps integration traffic inside the data centre — data never leaves Abu Dhabi.
SPEED OF DELIVERY
Very fast delivery, at the pace the business requires
• Agile — two-week sprints, inclusive of UAT and training.
• Six of eight modules already built and UAT-tested in the pilot environment.
• First go-live in week 3; a further module every two weeks.
COST
Lowest total cost
• USD 100,000 all-inclusive (~USD 12.5K per module) — deployment to hypercare.
• No per-user licensing — APEX / ORDS / JET runtimes licence-included.
• Market alternatives indicatively 5–10× the cost and 4–6× the duration.
iFinance Implementation Plan · DCT Finance Department · July 2026
4

## Slide 5
2 Solution Architecture
Finance staff — web (EN / AR)
Approvers — mobile app + push
Management — dashboards & BI
Freelancers — public portal
Single sign-on across all interfaces · role-based access · full audit trail
CORE42 DATA CENTRE — ABU DHABI
DCT iFinance — dedicated OCI tenancy
• Oracle Autonomous Database (data + business logic)
• APEX & ORDS REST services
• Web tier (application delivery)
• Integration runners — extract & write-back
• Reporting engines — scheduled PDF / Excel + interactive BI
ADERP — Oracle Fusion Cloud
• Government shared ERP instance
• Financials — GL, AP, PO / procurement
• Projects & budgets
• OTBI / BIP reporting layer (extract source)
Approved transactions (e.g. AP invoices)
Scheduled data extracts (GL, budgets, AP / PO / PR)
Single dedicated tenancy · integration traffic remains inside the data centre · all data resident in Abu Dhabi · government security baseline applied at provisioning
iFinance Implementation Plan · DCT Finance Department · July 2026
5

## Slide 6
3 Scope & Investment
USD 100,000 fixed quotation — eight business modules in delivery order, on a platform foundation included at no additional cost.
# | MODULE | WHAT IT DELIVERS | STATUS TODAY
1 | General Ledger | CoA classifications (sector / chapter / programme), budget-vs-actuals and budget-utilization reporting over ADERP data | Built & piloted
2 | Reporting & BI | Scheduled report distribution (PDF / Excel by email) and interactive self-service reports | Built & piloted
3 | Service Pricing | Pricing catalogue for DCT services — price definition, change approvals, effective-dated price lists (Sprint 2, with Reporting) | New build
4 | Freelancers | Registration (incl. public portal with AI-assisted document capture), contracts, vouchers, payments | Built & piloted
5 | Team Management | Team tasks, periodic reporting cycles, member check-ins, executive dashboards | Built & piloted
6 | Petty Cash | Custody, expenses, clearing & reimbursement with approvals; posts to Fusion AP | Built & piloted
7 | Duty Travel | Travel requests, per-diem calculation, approvals and settlement | Built & piloted
8 | Employee Housing | Housing allowance & accommodation requests, eligibility, approvals, payment instructions | New build
 | Platform foundation | Included: SSO, roles, delegations, audit, unified approvals inbox, notifications, bilingual EN / AR, mobile app | Included
The quotation is a one-time implementation cost. OCI tenancy infrastructure consumption is billed separately at the Core42 / ADGE rate card (procurement action, section 7).
iFinance Implementation Plan · DCT Finance Department · July 2026
6

## Slide 7
4 Options Comparison — Implementation Cost
USD, one-time implementation for a comparable 8-module scope. Alternatives are indicative market benchmark ranges; bar length shows the range midpoint.
A — iFinance on OCI @ Core42
recommended
USD 100K — fixed quotation · ≈ 3 months
B — Extend ADERP Fusion
custom PaaS extensions via SI
USD 0.7–1.4M indicative · 12–18 months
C — COTS point solutions
multiple products + integration
USD 0.5–0.9M indicative · 6–12 months
• Option A is ~10× lower cost than extending ADERP Fusion, and 4–6× faster than either alternative.
• No recurring application licences — APEX / ORDS / JET runtimes are included with the Oracle database.
iFinance Implementation Plan · DCT Finance Department · July 2026
7

## Slide 8
4 Options Comparison — Evaluation Criteria
 | A — iFINANCE ON OCI @ CORE42 (RECOMMENDED) | B — EXTEND ADERP FUSION | C — COTS POINT SOLUTIONS
Technology alignment | Full Oracle stack, same data centre as ADERP; aligned with ADGE direction | Oracle-aligned, but bound to the shared-instance change pipeline | Mixed vendors; new stacks to secure and support
Fusion integration | Both directions, already proven in pilot; in-data-centre traffic | Native, but every change is a central change request | Per-product connectors; typical gaps and duplication
Delivery time | ≈ 3 months; first go-live week 3, then every two weeks | 12–18 months typical | 6–12 months typical
Cost (indicative) | USD 100K fixed; no per-user licensing | USD 0.7–1.4M | USD 0.5–0.9M + recurring licences
Data residency | Abu Dhabi (Core42) — same facility as ADERP | Abu Dhabi (Core42) | Varies by vendor; assessed per product
Change speed after go-live | Days — DCT-controlled tenancy and codebase | Weeks–months via the shared change pipeline | Vendor roadmap dependent
iFinance Implementation Plan · DCT Finance Department · July 2026
8

## Slide 9
5 Implementation Timeline — Agile Delivery
Tenancy provisioned within one week of contract signature · seven two-week sprints delivering eight modules · go-live every two weeks from week 3 · full scope live by week 15 (≈ 3 months).
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
W11
W12
W13
W14
W15
Tenancy provisioning & platform foundation
W1
Sprint 1 · General Ledger
W2–3
Sprint 2 · Reporting & BI
W4–5
Sprint 2 · Service Pricing (new build)
W4–5
Sprint 3 · Freelancers
W6–7
Sprint 4 · Team Management
W8–9
Sprint 5 · Petty Cash
W10–11
Sprint 6 · Duty Travel
W12–13
Sprint 7 · Employee Housing (new build)
W14–15
Fusion integration · support · hypercare
W2–15 (continuous)
M1 Platform ready
M2 First module live (GL)
M3 5 of 8 modules live
M4 Full scope live & handover
Platform & integration workstream
Module delivery sprints (2 weeks each, incl. UAT & training)
Milestone
iFinance Implementation Plan · DCT Finance Department · July 2026
9

## Slide 10
5 Inside Each Two-Week Sprint
DAYS 1–2
Provision & configure
Module schema, REST services and organisation data set up on the tenancy.
DAYS 3–5
Adapt to DCT policy
Approval chains, delegation rules, GL mappings and reference data configured.
DAYS 6–7
Fusion integration
Extract feeds and write-back wiring connected and reconciled for the module.
DAYS 8–9
UAT & training
Structured UAT with the business owner; fixes applied; end-user training delivered.
DAY 10
Sign-off & go-live
Sprint review, formal sign-off and production go-live; retrospective feeds the next sprint.
Every sprint concludes with a working module in production — accepted by its business owner, with users trained and a documented UAT evidence pack.
iFinance Implementation Plan · DCT Finance Department · July 2026
10

## Slide 11
6 Governance & Quality
• Agile governance: sprint planning, sprint review and retrospective conducted with the module's business owner in every sprint.
• Executive oversight: fortnightly steering review with the Finance Director, aligned to sprint boundaries.
• Quality gates: formal sign-off at every sprint close, supported by a documented UAT evidence pack and delivered training material per module.
• Operational discipline: versioned deployment runbooks; government security baseline applied at tenancy provisioning; bilingual English / Arabic experience as a standard acceptance criterion.
iFinance Implementation Plan · DCT Finance Department · July 2026
11

## Slide 12
6 Risks & Mitigations
RISK | IMPACT | MITIGATION
Tenancy procurement lead time | Delays the entire critical path | Raise the Core42 / ADGE procurement immediately upon approval; provisioning completes within one week of contract signature.
Fusion integration access | Extract / posting cycles blocked | Request reporting-extract and posting access through ADGE at kick-off; a proven interim extract mechanism from the pilot covers any gap.
Business availability for UAT & training | Sprint sign-off slips | Fixed UAT and training window in the second week of each sprint, with a named business owner confirmed at sprint planning.
New-build scope drift (Service Pricing, Employee Housing) | A new-build module overruns its sprint | Requirements workshop and scope freeze before Sprint 2 and Sprint 7 respectively; both follow the proven platform pattern.
Security & residency compliance | Approval or audit findings | All data resident in Core42 Abu Dhabi; single dedicated tenancy; SSO, role-based access and full audit trail; security review at M1.
iFinance Implementation Plan · DCT Finance Department · July 2026
12

## Slide 13
7 Requested Approvals & Next Steps
1
Approve the recommended option and the USD 100,000 implementation budget for the eight-module scope.
2
Initiate procurement of the Oracle OCI tenancy in the Core42 data centre (same facility as ADERP) — the single critical-path action; provisioning completes within one week of contract signature.
3
Request Fusion integration access (reporting extracts and transaction posting) through ADGE, in parallel with procurement.
4
Nominate one business owner per module to lead UAT and receive training within each sprint.
5
Confirm kick-off — Sprint 1 (General Ledger) starts in week 2, with the first go-live in week 3.
iFinance Implementation Plan · DCT Finance Department · July 2026
13