## Instructions
i-Finance UAT — Task Management (App 207)
• Round 3 · 14-Jun-2026 · Environment: dev-proxy → ADB PROD.
• Round 3 focus: measurable objectives (OKR-style Key Results) — per-KR baseline/target/current with auto weighted progress roll-up, a MANUAL override, and full objective + key-result CRUD. Re-runs the full TM regression suite (teams, members, tasks, artifacts, cross-cutting) alongside it.
• Login: TM authenticates through the Admin portal — enter via the module switcher (shared session).
• Status legend: PASS / FAIL / PARTIAL / MANUAL / SKIP (Status column has a dropdown).
• Automated results with one evidence screenshot per case: UAT_TM_Results_14-Jun-2026-01.docx.

## Access & Session
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
TM-ACC-01 | Shared session | Entry from Admin via switcher | 1. Login in the Admin app 2. Open the module switcher 3. Choose Task Management | TM (App 207) opens logged-in with no second login; TM brand cube; role-appropriate nav | Not Run
TM-ACC-02 | No session | Direct open without login | 1. Logout / fresh private window 2. Open the TM app URL directly | Redirected to the Admin portal login; no TM content before login | Not Run
TM-ACC-03 | Role gating | Admin-only nav hidden for non-admin | 1. Enter TM as a non-admin user | Team Roles (admin) nav hidden for non-admins; Teams/My Tasks available | Not Run

## Dashboard
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
TM-DSH-01 | KPI tiles | Five live KPI tiles | 1. Open the TM dashboard | My Teams / My Open Tasks / Overdue / Open Issues & Risks / Deliverables Due tiles show live numbers | Not Run
TM-DSH-02 | Charts | Teams by Health + Class | 1. Open the dashboard and wait for charts | Both Chart.js charts render with data (no empty boxes) | Not Run

## Teams
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
TM-TMS-01 | List | Team grid loads | 1. Open Teams | Team cards show code, health RAG, type/class and member/task counts | Not Run
TM-TMS-02 | Filter | Type/class/status filters | 1. On Teams pick a Type filter | Grid re-queries server-side and shows matching teams | Not Run
TM-TMS-03 | Create | New team via platform modal | 1. Teams → New Team 2. Fill name, type, class, objective 3. Create | Team created with a TM- code; creator auto-enrolled as Leader; appears in the grid | Not Run

## Team Detail
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
TM-DTL-01 | Overview | Full team definition grid | 1. Open a team | Overview shows ALL team fields in an aligned definition grid + KPI tiles + 9 tabs | Not Run
TM-DTL-02 | Edit team | Edit Team modal persists | 1. Open a team → Edit Team 2. Change objective + status 3. Save Changes | Edit modal (top-right) saves via PUT; changes persist on reload | Not Run

## Objectives & Key Results
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
TM-OBJ-01 | Create objective | Measurable objective (AUTO) | 1. Objectives tab → Add Objective 2. Title + status 3. Save | Objective created and listed; progress defaults to AUTO (rolled up from key results) | Not Run
TM-OBJ-02 | KR increase | Add an INCREASE key result | 1. Open the objective → Add Key Result 2. Unit %, Increase, baseline 0, target 100, current 50 3. Save | KR shows 50%; the objective auto-progress rolls up to 50% | Not Run
TM-OBJ-03 | KR decrease + roll-up | Add a DECREASE key result | 1. Add a second KR: Decrease, baseline 100, target 0, current 75 | KR shows 25%; the objective weighted roll-up becomes 37.5% | Not Run
TM-OBJ-04 | Update measurement | Inline current-value update | 1. In the KR row set current = 100 2. Update | The objective auto-progress reflows live to 62.5% | Not Run
TM-OBJ-05 | Manual override | MANUAL pins the percentage | 1. Set the objective to Manual at 88% 2. Change a KR value | Objective stays 88% (KR changes no longer move it); switch back to Auto restores roll-up | Not Run
TM-OBJ-06 | Target required | KR without a target | 1. Add a KR with no target value | Rejected with HTTP 400 (boundary) | Not Run
TM-OBJ-07 | Invalid direction | Bad direction lookup | 1. Add a KR with an invalid direction | Rejected with HTTP 400 (lookup validation) | Not Run
TM-OBJ-08 | Permission | Non-member cannot add a KR | 1. As a non-member, add a KR | Denied with HTTP 403 (OBJECTIVE permission) | Not Run
TM-OBJ-09 | Delete objective | Cascade key results | 1. Remove an objective that has key results | Objective removed and its key results cascade away | Not Run

## Members
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
TM-MBR-01 | Add member | Add from the user picker | 1. Members tab → Add Member 2. Pick a user + role + title 3. Add | Member added from DCT_USERS and listed with avatar + role | Not Run
TM-MBR-02 | Change role | Inline role change | 1. Change a member’s role in the row dropdown | New team role persists | Not Run
TM-MBR-03 | Remove member | Remove from team | 1. Click remove on a member row | Member removed and no longer listed | Not Run

## Tasks
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
TM-TSK-01 | Create | Add a task | 1. Tasks tab → Add Task 2. Title, priority, status, due date 3. Save | Task created and shown on the Kanban board | Not Run
TM-TSK-02 | Kanban move | Move across columns | 1. Drag a card to another column (or change status) | Status changes and status history is written | Not Run
TM-TSK-03 | Assign | Assign a member | 1. Open a task drawer 2. Assign a team member as primary | Assignee shown in the drawer with a primary badge | Not Run
TM-TSK-04 | Reassign | Reassignment is tracked | 1. Set a different member as primary | Primary moves to the new member AND the activity feed logs the reassignment (audit trail) | Not Run
TM-TSK-05 | Comment | Activity feed comment | 1. Post a comment in the task drawer | Comment appears in the activity feed | Not Run

## Artifacts
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
TM-ART-01 | Deliverable | Add a deliverable | 1. Deliverables tab → Add | Deliverable created and listed | Not Run
TM-ART-02 | RAID | Add a RAID item | 1. RAID Log tab → Add (Risk, HIGH, OPEN) | RAID item created and listed | Not Run
TM-ART-03 | Milestone | Add a milestone | 1. Milestones tab → Add (due date, status) | Milestone created and listed | Not Run
TM-ART-04 | Meeting | Add a meeting | 1. Meetings tab → Add (date, location, agenda) | Meeting created and listed | Not Run
TM-ART-05 | Document | Add a team document | 1. Documents tab → Add Document 2. File/name + type + notes | Document stored in the unified store (source_module=TM) and listed | Not Run

## Cross-cutting
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
TM-XCT-01 | My Tasks | Cross-team assigned tasks | 1. Open My Tasks | Tasks assigned to me across all teams are listed | Not Run
TM-XCT-02 | Reports | Management reports catalogue | 1. Open Reports | The management report catalogue renders | Not Run
TM-XCT-03 | Preferences | Reminder preferences | 1. Open Preferences 2. Change lead-days and save | Lead-days preference saves and persists | Not Run
TM-XCT-04 | Language | EN ↔ AR RTL | 1. Switch language to Arabic | Shell flips RTL with Arabic labels; Latin digits retained | Not Run