## Instructions
i-Finance UAT — BI Reporting (App 211) — Interactive Reports platform
• Round 2 · 03-Jul-2026 · Environment: dev-proxy (8090) → ADB PROD ORDS.
• Scope: BI_USER viewer + spec-driven run parameters (PARAM_SPEC_JSON), shared <interactive-report> grid (control breaks, highlight rules, calc columns, layouts, exports, maximize), admin param-spec editor, ir/* API security.
• Users: NASER.ALKHAJA (BI_USER) · ADMIN (SYS_ADMIN).
• Evidence: evidence_03-Jul-2026-02/ — one file per case.

## Viewer & Parameters
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
BI-IRV-01 | Catalog | BI_USER opens the report catalog | 1. Log in as a BI_USER-only user 2. Open Interactive Reports | The catalog lists the enabled report definitions | PASS | Claude (automated) | 03-Jul-2026 | 3 catalog rows [01_biuser_catalog.png]
BI-IRV-02 | Access | Role-filtered navigation + admin reroute | 1. As BI_USER inspect the side nav 2. Navigate to #reports directly | Nav shows only Dashboard + Interactive Reports; the admin route reroutes away | PASS | Claude (automated) | 03-Jul-2026 | nav links=2, landed title='dashboard' [02_biuser_reroute.png]
BI-IRV-03 | Run parameters | Labels come from the parameter spec | 1. Open BUDGET_UTIL_SECTOR | Fields show "Budget Year", "Sector", "Project Type", "Cost Center" (not raw keys) | PASS | Claude (automated) | 03-Jul-2026 | section ¦ budget year * ¦ sector * ¦ project type ¦ cost center [03_param_labels.png]
BI-IRV-04 | Run parameters | LOV dropdowns are populated | 1. On BUDGET_UTIL_SECTOR wait for the parameter card | Year and Sector render as dropdowns with values | PASS | Claude (automated) | 03-Jul-2026 | selects=5 yearOpts=2 sectorOpts=12 [04_param_lovs.png]
BI-IRV-05 | Validation | Required parameters block the run | 1. Clear Year + Sector 2. Click Run | A warning names the missing required fields; no fetch happens | PASS | Claude (automated) | 03-Jul-2026 | toast='required parameter(s) missing: budget year, sector\n✕ required parameter(s) missing: budget year, sector\n✕ required parameter(s) missing: budget year, ' [05_required_warn.png]
BI-IRV-06 | Run parameters | Hints display under the fields | 1. Inspect the parameter card | The spec hints render under Year/Sector | PASS | Claude (automated) | 03-Jul-2026 | Required. The budget year the report covers (e.g. 2026). ¦ Required. The sector the report is generated for. ¦ Optional. Filter to one project type; leave empty to include all types. ¦ Optional. Filte [06_param_hints.png]
BI-IRV-07 | i18n | Arabic labels + RTL | 1. Switch the language to Arabic | Parameter labels show the Arabic spec labels; page flips RTL | PASS | Claude (automated) | 03-Jul-2026 | dir=rtl labels=القسم ¦ سنة الميزانية * ¦ القطاع * ¦ نوع المشروع ¦ مركز التكلفة [07_arabic_labels.png]
BI-IRV-08 | Data fetch | Run a report into the grid | 1. Open GL_BUDGET_ACTUAL 2. Click Run | The interactive grid renders the data rows | PASS | Claude (automated) | 03-Jul-2026 | 50 rows on page 1 [08_grid_rendered.png]

## Grid Features
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
BI-IRG-01 | Columns | Hide a column | 1. Columns panel 2. Untick the first column | The column leaves the grid | PASS | Claude (automated) | 03-Jul-2026 | 12 -> 11 headers [09_hide_column.png]
BI-IRG-02 | Columns | Reorder a column | 1. Columns panel 2. Move the first column down | Header order changes | PASS | Claude (automated) | 03-Jul-2026 | 'PERIOD NAME' -> 'SECTOR NAME' [10_reorder_column.png]
BI-IRG-03 | Columns | Rename a header | 1. Columns panel 2. Pencil on first column 3. Type "My Col", OK | Header shows the new label | PASS | Claude (automated) | 03-Jul-2026 | header='my col' [11_rename_header.png]
BI-IRG-04 | Filters | Add + remove a filter chip | 1. Add Filter (first col, is not empty) 2. Apply 3. Remove the chip | Chip appears; removing restores the count | PASS | Claude (automated) | 03-Jul-2026 | chips=1, '1–50 of 3697'->'1–50 of 3697' [12_filter_chip.png]
BI-IRG-05 | Sorting | Click-sort + Shift multi-sort | 1. Click header 1 2. Shift-click header 2 | Indexed sort badges appear | PASS | Claude (automated) | 03-Jul-2026 | badges=['▲1', '▲2'] [13_multi_sort.png]
BI-IRG-06 | Search | Global search narrows the results | 1. Type a non-matching term 2. Clear the box | Count drops to none, then restores | PASS | Claude (automated) | 03-Jul-2026 | '1–50 of 3697' -> 'No rows' -> '1–50 of 3697' [14_global_search.png]
BI-IRG-07 | Control breaks | Break groups the rows into bands | 1. Columns panel 2. Break on column 1 | Band rows show "Column: value"; a break chip appears | PASS | Claude (automated) | 03-Jul-2026 | bands=1 chips=1 [15_control_break.png]
BI-IRG-08 | Control breaks | Per-group subtotals + grand total | 1. Break also on the first numeric column 2. Set its aggregate to Sum | Subtotal rows appear at group ends; the grand-total footer stays | PASS | Claude (automated) | 03-Jul-2026 | subtotals=7 footerCells=12 [16_subtotals.png]
BI-IRG-09 | Highlight rules | Row-scope rule colors matching rows | 1. Highlight 2. Rule: col1 is not empty, whole row, green 3. Apply | Matching rows take the fill; the toolbar badge counts the rule | PASS | Claude (automated) | 03-Jul-2026 | styledRows=50 badge=1 [17_highlight_rule.png]
BI-IRG-10 | Calculated columns | Add a calculated column | 1. Columns panel > + Calculated column 2. Name TESTCALC, expr ROUND(1+1, 0) 3. Save | TESTCALC joins the grid with computed values | PASS | Claude (automated) | 03-Jul-2026 | headers=period name sector name program name account code account desc budget ytd encumbrance ytd gl actual ytd ap direct actual ytd grn actual ytd funds avai [18_calc_column.png]
BI-IRG-11 | Export | CSV + Excel export download | 1. Click CSV 2. Click Excel | Both files download | PASS | Claude (automated) | 03-Jul-2026 | GL_BUDGET_ACTUAL_20260703.csv + GL_BUDGET_ACTUAL_20260703.xlsx (lib=True) [19_exports.png]
BI-IRG-12 | Maximize | Fullscreen toggle + Esc restore | 1. Click the maximize arrow 2. Press Esc | Grid fills the screen; Esc restores | PASS | Claude (automated) | 03-Jul-2026 | maxed=True restored=True [20_maximized.png]
BI-IRG-13 | Layouts | Save / reset / apply round-trip (breaks + highlights + calc) | 1. Save as "UAT R2 Layout" 2. Reset view 3. Apply the layout 4. Delete it | Reset clears everything; Apply restores breaks, highlight, calc column | PASS | Claude (automated) | 03-Jul-2026 | cleared=True restored=True deleted=True [21_layout_roundtrip.png]

## Admin Param Spec
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
BI-IRA-01 | Spec editor | Parameters drawer opens prefilled | 1. Reports > BUDGET_UTIL_SECTOR > Open 2. Click Parameters | Drawer lists the 4 params; Year label prefilled "Budget Year" | PASS | Claude (automated) | 03-Jul-2026 | cards=4 yearLabel='Budget Year' [22_spec_drawer.png]
BI-IRA-02 | Spec editor | LOV Test button runs the query | 1. In the drawer click Test under the Year LOV | A value count + sample values display | PASS | Claude (automated) | 03-Jul-2026 | Run Parameters — labels, hints and lists of values [23_spec_test.png]
BI-IRA-03 | Spec editor | Save persists the spec | 1. Click Save on the drawer | Toast confirms; drawer closes; spec unchanged on the server | PASS | Claude (automated) | 03-Jul-2026 | closed=True specStable=True [24_spec_saved.png]
BI-IRA-04 | Run drawer | Run now still opens the LOV Run drawer (regression) | 1. Back to Reports 2. Run now on BUDGET_UTIL_SECTOR | The Run Parameters drawer opens with LOV dropdowns from the same spec | PASS | Claude (automated) | 03-Jul-2026 | drawer=0 lovSelects=4 [25_run_drawer.png]

## API & Security
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
BI-API-01 | ir/catalog | Catalog carries the spec-driven params[] | GET /rpt/ir/catalog as BI_USER | BUDGET_UTIL_SECTOR params[] has labels/required/hasLov | PASS | Claude (automated) | 03-Jul-2026 | status=200 params=['costcenter', 'projecttype', 'sector', 'year'] [26_api_catalog.txt]
BI-API-02 | ir/lov | LOV values served from PARAM_SPEC_JSON | GET ir/reports/GL_BUDGET_ACTUAL/lov?param=period | 200 + items; unknown param 400 | PASS | Claude (automated) | 03-Jul-2026 | 7 items / unknown=400 [27_api_lov.txt]
BI-API-03 | ir/paramspec | Spec editor endpoints are admin-only | GET+PUT ir/reports/:code/paramspec as BI_USER | Both return 403 | PASS | Claude (automated) | 03-Jul-2026 | GET=403 PUT=403 [28_api_paramspec_403.txt]
BI-API-04 | ir/lov/preview | Preview guards: query-only, bind-free, admin-only | POST ir/lov/preview with a DELETE, a :bind query, and as BI_USER | DELETE→400, bind→400, BI_USER→403; a clean SELECT→200 | PASS | Claude (automated) | 03-Jul-2026 | ok=200 del=400 bind=400 role=403 [29_api_preview_guards.txt]