## Slide 1
DEPARTMENT OF CULTURE AND TOURISM · FINANCE — i-FINANCE GL
Tourism Sector
Project Budget Utilization — FY2026
Executive briefing — budget vs. execution, open commitments and month-over-month delivery
Prepared 6 July 2026 · Source: i-Finance General Ledger — Budget Utilization (live)

## Slide 2
Executive summary
FY2026 project budget position — all figures AED, year-to-date through 6 July 2026
FY2026 · Tourism
APPROVED BUDGET
1.56B
140 projects · 8 cost centres
ACTUAL SPEND
568.1M
36.3% utilised (GRN 563M + AP 5M)
OPEN COMMITMENTS (PR)
124.4M
reserved requisitions
OPEN OBLIGATIONS (PO)
250.6M
orders awaiting delivery
FUNDS AVAILABLE
620.9M
39.7% of budget uncommitted
How the budget sits today
▪ 60% of the budget is already deployed or spoken for — actual 568.1M (36.3%) plus 375.0M of open PR/PO commitments leave 620.9M genuinely free.
▪ Execution is procurement-led — over 99% of actual spend arrives through goods/services receipts (GRN) rather than direct invoices — delivery follow-through drives utilisation.
▪ Concentration — Tourism (Central) holds 76% of the sector budget; its execution pattern defines the sector curve.

## Slide 3
Budget by cost centre
Approved budget (track) vs. actual spend and open commitments — AED
FY2026 · Tourism
Bars show each cost centre’s full budget (grey track); coloured segments are actual spend and open PR/PO within it. Budget value at bar end.

## Slide 4
Utilisation ranking
Share of each cost centre’s own budget — utilised, reserved (PR) and on order (PO)
FY2026 · Tourism
Dashed line = sector utilisation (36.3%). A low utilised share with a large amber/indigo block means the pipeline is committed but not yet delivered.

## Slide 5
Month-over-month execution
Monthly actual spend (GRN + AP direct) with cumulative curve — AED
FY2026 · Tourism
* July is month-to-date (through 6 Jul). March reflects a major receipt cycle at Tourism (Central) — execution lands in steps as deliveries are receipted, not in a straight line.

## Slide 6
Tourism (Central)
Cost centre 4515500 · 51 projects · deep dive
FY2026 · Tourism
BUDGET
1.20B
76.5% of sector
ACTUAL
462.7M
38.7% utilised
OPEN PR
33.8M
2.8% of budget
OPEN PO
218.6M
18.3% of budget
AVAILABLE
480.8M
40.2% of budget
Budget composition
Monthly execution (AED)
Top projects by budget
Project | Budget | Actual | Committed (PR+PO) | Available
4511000725 — NBA- Basket Ball Development | 148.1M | 59.2M | 76.0M | 12.8M
4511000809 — Liwa Festival | 138.1M | 35.6M | 22.0M | 80.4M
4511000403 — TS - EB - G21 - M JV | 126.5M | 103.0M | 0 | 23.5M
4511000386 — TS - EB- UFC | 107.7M | 36.7M | 59.3M | 11.7M
4511001136 — Saadiyat Festival | 107.2M | 88.3M | 7.9M | 10.9M

## Slide 7
International Operations
Cost centre 4515100 · 12 projects · deep dive
FY2026 · Tourism
BUDGET
125.8M
8.0% of sector
ACTUAL
31.3M
24.9% utilised
OPEN PR
37.3M
29.6% of budget
OPEN PO
15.7M
12.4% of budget
AVAILABLE
41.5M
33.0% of budget
Budget composition
Monthly execution (AED)
Top projects by budget
Project | Budget | Actual | Committed (PR+PO) | Available
4511001474 — Exhibitions | 27.6M | 13.9M | 1.1M | 12.5M
4511000572 — TTMD Global Partnerships | 21.8M | 2.0M | 18.6M | 1.2M
4511001472 — Europe-Tier-1 | 15.1M | 4.0M | 5.0M | 6.0M
4511001471 — APAC-Tier-1 | 14.0M | 1.2M | 7.0M | 5.8M
4511001475 — Europe-Tier-2 | 12.5M | 2.8M | 3.5M | 6.2M

## Slide 8
Abu Dhabi Conventions & Exhibition Bureau
Cost centre 4515400 · 31 projects · deep dive
FY2026 · Tourism
BUDGET
77.0M
4.9% of sector
ACTUAL
22.8M
29.6% utilised
OPEN PR
11.1M
14.4% of budget
OPEN PO
4.3M
5.6% of budget
AVAILABLE
38.9M
50.5% of budget
Budget composition
Monthly execution (AED)
Top projects by budget
Project | Budget | Actual | Committed (PR+PO) | Available
4511000981 — Advantage AD Scheme | 48.3M | 14.9M | 6.3M | 27.1M
4511000798 — Develop Meeting & Incentives | 9.0M | 5.3M | 487K | 3.3M
4511001506 — Abu Dhabi MICE Strategy Refresh | 5.5M | 0 | 3.0M | 2.5M
4511000175 — TS-PRO-IMEX | 4.8M | 1.8M | 2.4M | 506K
4511000943 — B.D - Association Convention | 1.4M | 426K | 406K | 604K

## Slide 9
Visitor Experience & Tourism Products Development
Cost centre 4515300 · 14 projects · deep dive
FY2026 · Tourism
BUDGET
62.1M
4.0% of sector
ACTUAL
1.6M
2.6% utilised
OPEN PR
30.2M
48.6% of budget
OPEN PO
1.3M
2.2% of budget
AVAILABLE
28.9M
46.6% of budget
Budget composition
Monthly execution (AED)
Top projects by budget
Project | Budget | Actual | Committed (PR+PO) | Available
4511001537 — VX Signature Moments | 17.9M | 0 | 7.0M | 10.9M
4511000978 — Service standards Manual | 10.1M | 359K | 2.5M | 7.3M
4511001539 — VX Incentives & Control | 7.7M | 0 | 6.6M | 1.1M
4511001005 — VX consultancy services | 7.0M | 153K | 6.4M | 443K
4511001536 — VX Award | 4.6M | 144K | 3.6M | 854K

## Slide 10
Destination Management
Cost centre 4515700 · 4 projects · deep dive
FY2026 · Tourism
BUDGET
50.3M
3.2% of sector
ACTUAL
26.4M
52.5% utilised
OPEN PR
1.1M
2.3% of budget
OPEN PO
10.2M
20.4% of budget
AVAILABLE
12.5M
24.9% of budget
Budget composition
Monthly execution (AED)
Top projects by budget
Project | Budget | Actual | Committed (PR+PO) | Available
4511000860 — Al Ain Destination Strategy | 24.9M | 7.3M | 7.3M | 10.3M
4511001332 — GHAITAH ALAIN | 21.0M | 17.6M | 3.4M | 0
4511001235 — Shuttle bus across Tourist | 3.0M | 692K | 556K | 1.8M
4511000245 — MC-Abu Dhabi Destination | 1.4M | 797K | 199K | 398K

## Slide 11
Tourism Products Development
Cost centre 4515900 · 13 projects · deep dive
FY2026 · Tourism
BUDGET
34.3M
2.2% of sector
ACTUAL
21.7M
63.1% utilised
OPEN PR
6.0M
17.4% of budget
OPEN PO
338K
1.0% of budget
AVAILABLE
6.4M
18.5% of budget
Budget composition
Monthly execution (AED)
Top projects by budget
Project | Budget | Actual | Committed (PR+PO) | Available
4511001456 — Home Based Oper. - Air Arabia | 18.5M | 18.1M | 0 | 400K
4511000942 — Destination Wedding | 8.9M | 757K | 4.5M | 3.7M
4511001208 — Exhibition - Monaco Yacht Show | 1.5M | 1.2M | 280K | 21K
4511000935 — Cruise Partnerships | 806K | 186K | 222K | 398K
4511001128 — Product Development-Consultant | 757K | 454K | 0 | 303K

## Slide 12
Tourism (Central) (Office)
Cost centre 4515010 · 13 projects · deep dive
FY2026 · Tourism
BUDGET
15.5M
1.0% of sector
ACTUAL
1.4M
9.2% utilised
OPEN PR
3.7M
23.8% of budget
OPEN PO
135K
0.9% of budget
AVAILABLE
10.2M
66.1% of budget
Budget composition
Monthly execution (AED)
Top projects by budget
Project | Budget | Actual | Committed (PR+PO) | Available
4511001134 — Investment-Investor Pitch Book | 4.4M | 0 | 178K | 4.2M
4511000826 — TSM-Sector Management | 4.0M | 1.3M | 95K | 2.6M
4511000972 — Tourism Tactical research | 2.2M | 0 | 322K | 1.9M
4511000809 — Liwa Festival | 1.7M | 0 | 1.6M | 82K
4511001399 — Tourism Sustainability | 1.1M | 0 | 1.1M | 0

## Slide 13
Emiratization & Capability Development Office
Cost centre 4515020 · 3 projects · deep dive
FY2026 · Tourism
BUDGET
3.2M
0.2% of sector
ACTUAL
240K
7.5% utilised
OPEN PR
1.3M
40.2% of budget
OPEN PO
10K
0.3% of budget
AVAILABLE
1.7M
52.0% of budget
Budget composition
Monthly execution (AED)
Top projects by budget
Project | Budget | Actual | Committed (PR+PO) | Available
4511001405 — Strategic Emiratization | 2.3M | 240K | 1.1M | 925K
4511001404 — Industrial Professional Dev. | 765K | 0 | 33K | 733K
4511001406 — Emiratization Market Campaings | 150K | 0 | 150K | 0

## Slide 14
Observations & recommended actions
What the numbers say — and where management attention pays off
FY2026 · Tourism
▪ Concentration risk — Tourism (Central) carries 76% of the sector budget (1.20B); sector delivery is effectively this cost centre’s delivery. Recommend a dedicated monthly delivery review for its top-5 projects.
▪ Committed but not delivered = 375.0M (24% of budget) — PO 250.6M awaiting receipts plus PR 124.4M awaiting conversion. Utilisation will step up mechanically as deliveries land — push GRN discipline (receipt on delivery, not at invoice time).
▪ Pipeline stuck at requisition — Visitor Experience & Tourism Products Development is only 3% utilised, yet 49% of its budget (30.2M) is already reserved on requisitions — expedite PR→PO conversion and delivery scheduling.
▪ Run-rate check — actual spend averages ≈ 91.6M/month. With 620.9M free and 375.0M committed, full-year consumption projects close to budget only if committed orders deliver in H2 — track PO ageing monthly.
▪ Low-utilisation watchlist — Tourism Central Office (8.0%) and Emiratization (7.5%) — small budgets, but if unspent by Q3 they are reallocation candidates.
▪ Healthy signal — only 5.1M (0.3%) of spend bypasses procurement as direct AP — strong contract/PO discipline across the sector.

## Slide 15
Appendix — definitions & method
How each figure is derived (all AED, FY2026)
FY2026 · Tourism
▪ Approved budget — FY2026 project budget per Project × Task × Expenditure Type (Fusion projects budget extract).
▪ Actual — GRN received — value of goods/services receipted against purchase orders (receipt date in FY2026).
▪ Actual — AP direct — validated supplier invoices charged directly to a project with no purchase order.
▪ Open commitments (PR) — requisition lines with funds status Reserved — budget held, order not yet placed.
▪ Open obligations (PO) — purchase-order lines Reserved / Partially Liquidated, net of receipts to date.
▪ Funds available — Budget − Actual AP − Actual GRN − Open PR − Open PO.
▪ Source — i-Finance General Ledger (App 210) — Budget Utilization report over DCT_BUDGET_UTILIZATION_V; monthly split reconciles to the report’s drill-down. Data as of 6 July 2026; July is month-to-date.