## Instructions
i-Finance UAT — Task Management (App 207)
• Round 2 · 13-Jun-2026 · Environment: dev-proxy → ADB PROD.
• Scope: UI/UX rework to the shared platform design + functional enhancements (team edit, member management, task assignment with reassignment tracking, milestones, meetings, documents).
• Login: TM authenticates through the Admin portal — enter via the module switcher (shared session).
• Status legend: PASS / FAIL / PARTIAL / MANUAL / SKIP (Status column has a dropdown).
• Automated results with one evidence screenshot per case: UAT_TM_Results_13-Jun-2026-01.docx.

## Access & Session
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
TM-ACC-01 | Shared session | Entry from Admin via switcher | 1. Login in the Admin app 2. Open the module switcher 3. Choose Task Management | TM (App 207) opens logged-in with no second login; TM brand cube; role-appropriate nav | PASS | Claude (automated) | 13-Jun-2026 | Admin login → module switcher → TM (App 207) opened logged-in, no second login
TM-ACC-02 | No session | Direct open without login | 1. Logout / fresh private window 2. Open the TM app URL directly | Redirected to the Admin portal login; no TM content before login | PASS | Claude (automated) | 13-Jun-2026 | TM opened without a session redirected to the Admin portal login
TM-ACC-03 | Role gating | Admin-only nav hidden for non-admin | 1. Enter TM as a non-admin user | Team Roles (admin) nav hidden for non-admins; Teams/My Tasks available | PASS | Claude (automated) | 13-Jun-2026 | Non-admin (SHAIKHA.GALAMERI) enters TM via shared session; Team Roles admin nav hidden

## Dashboard
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
TM-DSH-01 | KPI tiles | Five live KPI tiles | 1. Open the TM dashboard | My Teams / My Open Tasks / Overdue / Open Issues & Risks / Deliverables Due tiles show live numbers | PASS | Claude (automated) | 13-Jun-2026 | 5 KPI tiles render: 12, 0, 0, 2, 0
TM-DSH-02 | Charts | Teams by Health + Class | 1. Open the dashboard and wait for charts | Both Chart.js charts render with data (no empty boxes) | PASS | Claude (automated) | 13-Jun-2026 | Teams-by-Health + Teams-by-Class charts rendered (2 canvases)

## Teams
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
TM-TMS-01 | List | Team grid loads | 1. Open Teams | Team cards show code, health RAG, type/class and member/task counts | PASS | Claude (automated) | 13-Jun-2026 | Teams grid shows 1 card(s); API total=12
TM-TMS-02 | Filter | Type/class/status filters | 1. On Teams pick a Type filter | Grid re-queries server-side and shows matching teams | PASS | Claude (automated) | 13-Jun-2026 | Type filter applied (INTERNAL); grid re-queried server-side
TM-TMS-03 | Create | New team via platform modal | 1. Teams → New Team 2. Fill name, type, class, objective 3. Create | Team created with a TM- code; creator auto-enrolled as Leader; appears in the grid | PASS | Claude (automated) | 13-Jun-2026 | Team "UAT TM Team 000815" created (TM-2026-00016) via the platform modal; leader auto-enrolled

## Team Detail
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
TM-DTL-01 | Overview | Full team definition grid | 1. Open a team | Overview shows ALL team fields in an aligned definition grid + KPI tiles + 9 tabs | PASS | Claude (automated) | 13-Jun-2026 | Overview shows full team definition grid (14 fields) + KPI tiles; 9 tabs present
TM-DTL-02 | Edit team | Edit Team modal persists | 1. Open a team → Edit Team 2. Change objective + status 3. Save Changes | Edit modal (top-right) saves via PUT; changes persist on reload | PASS | Claude (automated) | 13-Jun-2026 | Edit Team modal saved: objective updated + status=ON_HOLD (persisted via PUT)

## Members
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
TM-MBR-01 | Add member | Add from the user picker | 1. Members tab → Add Member 2. Pick a user + role + title 3. Add | Member added from DCT_USERS and listed with avatar + role | PASS | Claude (automated) | 13-Jun-2026 | Added Ayesha Al Ameri as MEMBER via the user picker; members table shows 2 rows
TM-MBR-02 | Change role | Inline role change | 1. Change a member’s role in the row dropdown | New team role persists | PASS | Claude (automated) | 13-Jun-2026 | Ayesha Al Ameri role changed MEMBER → COORDINATOR (persisted)
TM-MBR-03 | Remove member | Remove from team | 1. Click remove on a member row | Member removed and no longer listed | PASS | Claude (automated) | 13-Jun-2026 | Added then removed Hany; member no longer listed

## Tasks
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
TM-TSK-01 | Create | Add a task | 1. Tasks tab → Add Task 2. Title, priority, status, due date 3. Save | Task created and shown on the Kanban board | PASS | Claude (automated) | 13-Jun-2026 | Task created (HIGH, due +5d); appears on the Kanban TODO column
TM-TSK-02 | Kanban move | Move across columns | 1. Drag a card to another column (or change status) | Status changes and status history is written | PASS | Claude (automated) | 13-Jun-2026 | Task moved TODO → IN_PROGRESS (status history written); reflected on the board
TM-TSK-03 | Assign | Assign a member | 1. Open a task drawer 2. Assign a team member as primary | Assignee shown in the drawer with a primary badge | PASS | Claude (automated) | 13-Jun-2026 | Assigned Ayesha Al Ameri as primary; assignee shown in the task drawer
TM-TSK-04 | Reassign | Reassignment is tracked | 1. Set a different member as primary | Primary moves to the new member AND the activity feed logs the reassignment (audit trail) | PASS | Claude (automated) | 13-Jun-2026 | Primary reassigned to Hany; activity feed logged: "Primary assignee reassigned from AYESHA.AMERI to HANY"
TM-TSK-05 | Comment | Activity feed comment | 1. Post a comment in the task drawer | Comment appears in the activity feed | PASS | Claude (automated) | 13-Jun-2026 | Comment posted to the task activity feed and listed

## Artifacts
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
TM-ART-01 | Deliverable | Add a deliverable | 1. Deliverables tab → Add | Deliverable created and listed | PASS | Claude (automated) | 13-Jun-2026 | Deliverable added and listed on the Deliverables tab
TM-ART-02 | RAID | Add a RAID item | 1. RAID Log tab → Add (Risk, HIGH, OPEN) | RAID item created and listed | PASS | Claude (automated) | 13-Jun-2026 | RAID risk (HIGH/OPEN) added and listed on the RAID Log tab
TM-ART-03 | Milestone | Add a milestone | 1. Milestones tab → Add (due date, status) | Milestone created and listed | PASS | Claude (automated) | 13-Jun-2026 | Milestone added (due +14d, PENDING) and listed on the Milestones tab
TM-ART-04 | Meeting | Add a meeting | 1. Meetings tab → Add (date, location, agenda) | Meeting created and listed | PASS | Claude (automated) | 13-Jun-2026 | Meeting added (date +3d, Room 1) and listed on the Meetings tab
TM-ART-05 | Document | Add a team document | 1. Documents tab → Add Document 2. File/name + type + notes | Document stored in the unified store (source_module=TM) and listed | PASS | Claude (automated) | 13-Jun-2026 | Document added to the team (unified DCT_DOCUMENTS, source_module=TM) and listed

## Cross-cutting
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
TM-XCT-01 | My Tasks | Cross-team assigned tasks | 1. Open My Tasks | Tasks assigned to me across all teams are listed | PASS | Claude (automated) | 13-Jun-2026 | My Tasks page loads ("My Tasks"); cross-team assigned tasks listed (API items=0)
TM-XCT-02 | Reports | Management reports catalogue | 1. Open Reports | The management report catalogue renders | PASS | Claude (automated) | 13-Jun-2026 | Management Reports page renders the report catalogue
TM-XCT-03 | Preferences | Reminder preferences | 1. Open Preferences 2. Change lead-days and save | Lead-days preference saves and persists | PASS | Claude (automated) | 13-Jun-2026 | Reminder preferences page loads; lead-days saved (5) and restored
TM-XCT-04 | Language | EN ↔ AR RTL | 1. Switch language to Arabic | Shell flips RTL with Arabic labels; Latin digits retained | PASS | Claude (automated) | 13-Jun-2026 | EN→AR flips the shell to RTL with Arabic labels; numbers stay Latin digits; restored to EN