## Instructions
i-Finance UAT — BI Reporting (App 211) — Interactive Reports platform
• Round 2 · 03-Jul-2026 · Environment: dev-proxy (8090) → ADB PROD ORDS.
• Scope: BI_USER viewer + spec-driven run parameters (PARAM_SPEC_JSON), shared <interactive-report> grid (control breaks, highlight rules, calc columns, layouts, exports, maximize), admin param-spec editor, ir/* API security.
• Users: NASER.ALKHAJA (BI_USER) · ADMIN (SYS_ADMIN).
• Evidence: evidence_03-Jul-2026-02/ — one file per case.

## Viewer & Parameters
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
BI-IRV-01 | Catalog | BI_USER opens the report catalog | 1. Log in as a BI_USER-only user 2. Open Interactive Reports | The catalog lists the enabled report definitions
BI-IRV-02 | Access | Role-filtered navigation + admin reroute | 1. As BI_USER inspect the side nav 2. Navigate to #reports directly | Nav shows only Dashboard + Interactive Reports; the admin route reroutes away
BI-IRV-03 | Run parameters | Labels come from the parameter spec | 1. Open BUDGET_UTIL_SECTOR | Fields show "Budget Year", "Sector", "Project Type", "Cost Center" (not raw keys)
BI-IRV-04 | Run parameters | LOV dropdowns are populated | 1. On BUDGET_UTIL_SECTOR wait for the parameter card | Year and Sector render as dropdowns with values
BI-IRV-05 | Validation | Required parameters block the run | 1. Clear Year + Sector 2. Click Run | A warning names the missing required fields; no fetch happens
BI-IRV-06 | Run parameters | Hints display under the fields | 1. Inspect the parameter card | The spec hints render under Year/Sector
BI-IRV-07 | i18n | Arabic labels + RTL | 1. Switch the language to Arabic | Parameter labels show the Arabic spec labels; page flips RTL
BI-IRV-08 | Data fetch | Run a report into the grid | 1. Open GL_BUDGET_ACTUAL 2. Click Run | The interactive grid renders the data rows

## Grid Features
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
BI-IRG-01 | Columns | Hide a column | 1. Columns panel 2. Untick the first column | The column leaves the grid
BI-IRG-02 | Columns | Reorder a column | 1. Columns panel 2. Move the first column down | Header order changes
BI-IRG-03 | Columns | Rename a header | 1. Columns panel 2. Pencil on first column 3. Type "My Col", OK | Header shows the new label
BI-IRG-04 | Filters | Add + remove a filter chip | 1. Add Filter (first col, is not empty) 2. Apply 3. Remove the chip | Chip appears; removing restores the count
BI-IRG-05 | Sorting | Click-sort + Shift multi-sort | 1. Click header 1 2. Shift-click header 2 | Indexed sort badges appear
BI-IRG-06 | Search | Global search narrows the results | 1. Type a non-matching term 2. Clear the box | Count drops to none, then restores
BI-IRG-07 | Control breaks | Break groups the rows into bands | 1. Columns panel 2. Break on column 1 | Band rows show "Column: value"; a break chip appears
BI-IRG-08 | Control breaks | Per-group subtotals + grand total | 1. Break also on the first numeric column 2. Set its aggregate to Sum | Subtotal rows appear at group ends; the grand-total footer stays
BI-IRG-09 | Highlight rules | Row-scope rule colors matching rows | 1. Highlight 2. Rule: col1 is not empty, whole row, green 3. Apply | Matching rows take the fill; the toolbar badge counts the rule
BI-IRG-10 | Calculated columns | Add a calculated column | 1. Columns panel > + Calculated column 2. Name TESTCALC, expr ROUND(1+1, 0) 3. Save | TESTCALC joins the grid with computed values
BI-IRG-11 | Export | CSV + Excel export download | 1. Click CSV 2. Click Excel | Both files download
BI-IRG-12 | Maximize | Fullscreen toggle + Esc restore | 1. Click the maximize arrow 2. Press Esc | Grid fills the screen; Esc restores
BI-IRG-13 | Layouts | Save / reset / apply round-trip (breaks + highlights + calc) | 1. Save as "UAT R2 Layout" 2. Reset view 3. Apply the layout 4. Delete it | Reset clears everything; Apply restores breaks, highlight, calc column

## Admin Param Spec
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
BI-IRA-01 | Spec editor | Parameters drawer opens prefilled | 1. Reports > BUDGET_UTIL_SECTOR > Open 2. Click Parameters | Drawer lists the 4 params; Year label prefilled "Budget Year"
BI-IRA-02 | Spec editor | LOV Test button runs the query | 1. In the drawer click Test under the Year LOV | A value count + sample values display
BI-IRA-03 | Spec editor | Save persists the spec | 1. Click Save on the drawer | Toast confirms; drawer closes; spec unchanged on the server
BI-IRA-04 | Run drawer | Run now still opens the LOV Run drawer (regression) | 1. Back to Reports 2. Run now on BUDGET_UTIL_SECTOR | The Run Parameters drawer opens with LOV dropdowns from the same spec

## API & Security
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
BI-API-01 | ir/catalog | Catalog carries the spec-driven params[] | GET /rpt/ir/catalog as BI_USER | BUDGET_UTIL_SECTOR params[] has labels/required/hasLov
BI-API-02 | ir/lov | LOV values served from PARAM_SPEC_JSON | GET ir/reports/GL_BUDGET_ACTUAL/lov?param=period | 200 + items; unknown param 400
BI-API-03 | ir/paramspec | Spec editor endpoints are admin-only | GET+PUT ir/reports/:code/paramspec as BI_USER | Both return 403
BI-API-04 | ir/lov/preview | Preview guards: query-only, bind-free, admin-only | POST ir/lov/preview with a DELETE, a :bind query, and as BI_USER | DELETE→400, bind→400, BI_USER→403; a clean SELECT→200

## Storage maintenance
ID | Suite | Check | Status | Evidence
BI-ST-001 | Browser edge and language checks | Storage figures render | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-002 | Browser edge and language checks | Retention displayed | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-003 | Browser edge and language checks | Largest reports displayed | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-004 | Browser edge and language checks | Audit has exact removed size | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-005 | Browser edge and language checks | Worker polling does not repeatedly scan storage | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-006 | Browser edge and language checks | Manual refresh reloads storage | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-007 | Browser edge and language checks | en no untranslated storage keys | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-008 | Browser edge and language checks | en fits 1535px | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-009 | Browser edge and language checks | en fits 768px | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-010 | Browser edge and language checks | en fits 390px | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-011 | Browser edge and language checks | ar no untranslated storage keys | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-012 | Browser edge and language checks | ar fits 1535px | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-013 | Browser edge and language checks | ar fits 768px | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-014 | Browser edge and language checks | ar fits 390px | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-015 | Browser edge and language checks | Failure shown without losing previous data | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-016 | Browser edge and language checks | Empty reports and audit states | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-017 | Browser edge and language checks | Keep-forever state renders | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-018 | Browser edge and language checks | Failed banner clears on retry | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-019 | Browser edge and language checks | Failed cleanup visible | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-020 | Browser edge and language checks | Error text safely escaped | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-021 | Browser edge and language checks | No JavaScript errors | NOT RUN | evidence_06-Sep-2026-01/deployed-browser/results.json
BI-ST-022 | Live API and access | Storage panel loads real data | NOT RUN | evidence_06-Sep-2026-01/deployed-live/results.json
BI-ST-023 | Live API and access | Authenticated storage API returns 200 | NOT RUN | evidence_06-Sep-2026-01/deployed-live/results.json
BI-ST-024 | Live API and access | Retention remains 90 days | NOT RUN | evidence_06-Sep-2026-01/deployed-live/results.json
BI-ST-025 | Live API and access | Storage totals are plausible | NOT RUN | evidence_06-Sep-2026-01/deployed-live/results.json
BI-ST-026 | Live API and access | Cleanup audit is present | NOT RUN | evidence_06-Sep-2026-01/deployed-live/results.json
BI-ST-027 | Live API and access | At most 10 largest reports and 20 audits | NOT RUN | evidence_06-Sep-2026-01/deployed-live/results.json
BI-ST-028 | Live API and access | File bytes reconcile with all listed reports when fewer than 10 | NOT RUN | evidence_06-Sep-2026-01/deployed-live/results.json
BI-ST-029 | Live API and access | Anonymous storage API blocked | NOT RUN | evidence_06-Sep-2026-01/deployed-live/results.json
BI-ST-030 | Live API and access | Existing scheduler controls still list maintenance | NOT RUN | evidence_06-Sep-2026-01/deployed-live/results.json
BI-ST-031 | Live API and access | Non-admin storage API blocked | NOT RUN | evidence_06-Sep-2026-01/deployed-live/results.json
BI-ST-032 | Database cleanup | Retention unchanged at 90 | NOT RUN | evidence_06-Sep-2026-01/db-test.log
BI-ST-033 | Database cleanup | No real outputs eligible before fixture | NOT RUN | evidence_06-Sep-2026-01/db-test.log
BI-ST-034 | Database cleanup | Only expired fixture removed | NOT RUN | evidence_06-Sep-2026-01/db-test.log
BI-ST-035 | Database cleanup | Run history preserved | NOT RUN | evidence_06-Sep-2026-01/db-test.log
BI-ST-036 | Database cleanup | Audit records success and exact file count | NOT RUN | evidence_06-Sep-2026-01/db-test.log
BI-ST-037 | Database cleanup | Audit records exact bytes | NOT RUN | evidence_06-Sep-2026-01/db-test.log
BI-ST-038 | Database cleanup | Audit records timing and policy | NOT RUN | evidence_06-Sep-2026-01/db-test.log
BI-ST-039 | Database cleanup | All real outputs preserved | NOT RUN | evidence_06-Sep-2026-01/db-test.log
BI-ST-040 | Database cleanup | Repeated cleanup safely records zero deletions | NOT RUN | evidence_06-Sep-2026-01/db-test.log
BI-ST-041 | Database cleanup | Exactly one enabled maintenance schedule | NOT RUN | evidence_06-Sep-2026-01/db-test.log
BI-ST-042 | Database cleanup | BI-managed ADMIN schedule retained | NOT RUN | evidence_06-Sep-2026-01/db-test.log
BI-ST-SCHED | Scheduler | New audited procedure executed successfully on the retained 15-minute ADMIN schedule; duplicate disabled | NOT RUN | evidence_06-Sep-2026-01/final-check.log