## Instructions
i-Finance UAT — Analytics Loader (App 208)
• Round 1 · 18-Jun-2026 · Environment: dev-proxy -> ADB PROD.
• Scope: the OTBI->ATD control plane (atd.rest) — dashboard, jobs CRUD + enqueue/reset, queue ops (enqueue-all/reap), run logs + CSV export, environments + targets CRUD, and the UI-managed Runner Settings (ATD_RUNNER_CONFIG). Covers Happy / Edge / Error(400/401/403) / Boundary.
• Login: ATD authenticates through the Admin portal — enter via the module switcher (shared session).
• Admin-only: every endpoint requires SYS_ADMIN; a non-admin is blocked with HTTP 403.
• Status legend: PASS / FAIL / PARTIAL / MANUAL / SKIP (Status column has a dropdown).
• Automated results with one evidence screenshot per case: UAT_ATD_Results_18-Jun-2026-01.docx.

## Access & Session
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ATD-ACC-01 | Shared session | Entry from Admin via switcher | 1. Login in the Admin app 2. Open the module switcher 3. Choose Analytics Loader | ATD (App 208) opens logged-in with no second login; AT brand cube; admin nav | Not Run
ATD-ACC-02 | No session | Direct open without login | 1. Fresh window 2. Open the ATD app URL directly | Redirected to the Admin portal login; no ATD content before login | Not Run
ATD-ACC-03 | Admin gating | Non-admin blocked from the API | 1. Call /atd/jobs as a non-admin (CC_ADMIN) | Denied with HTTP 403 (SYS_ADMIN required) | Not Run

## Dashboard
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ATD-DSH-01 | KPI tiles | Five live KPI tiles | 1. Open the ATD dashboard | Jobs / Enabled / Success Rate / Runs(24h) / Last Finished tiles show live numbers | Not Run
ATD-DSH-02 | Charts | Queue donut + recent/alerts | 1. Open the dashboard and wait for the chart | Queue-state donut renders; recent-runs and alerts tables populate | Not Run

## Jobs
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ATD-JOB-01 | List | Job grid loads | 1. Open Jobs | Grid shows job, source, target, order, status, last run | Not Run
ATD-JOB-02 | Create | New job via drawer/ORDS | 1. Jobs → New Job 2. Fill name, env, target, source, stage 3. Create | Job created and retrievable; appears in the grid | Not Run
ATD-JOB-03 | Edit | Edit persists | 1. Edit a job → change priority → Save | Change persists on reload (PUT) | Not Run
ATD-JOB-04 | Duplicate | Duplicate name rejected | 1. Create a job with an existing name | Rejected with HTTP 400 (boundary) | Not Run
ATD-JOB-05 | Enqueue | Mark READY | 1. Enqueue a job | run_status becomes READY (a worker would pick it up) | Not Run
ATD-JOB-06 | Delete | Remove a job | 1. Delete the job | Job removed; GET returns 404 (history kept) | Not Run

## Job Detail
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ATD-DTL-01 | Detail | Config + run history | 1. Open a job | Detail shows all config fields + run-history table | Not Run

## Queue & Ops
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ATD-QUE-01 | Enqueue all | Queue every enabled job | 1. Queue → Enqueue All | All enabled jobs marked READY | Not Run
ATD-QUE-02 | Reap stale | Reclaim stale leases | 1. Queue → Reap Stale | Stale CLAIMED jobs returned to READY (count reported) | Not Run

## Run Logs
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ATD-RUN-01 | List | Run log loads | 1. Open Run Logs | Filterable run log lists rows with status/rows/timestamps | Not Run
ATD-RUN-02 | Detail | Run detail modal | 1. Open a run | Detail returns message + checksum; modal opens | Not Run
ATD-RUN-03 | Export | CSV export | 1. Run Logs → Export CSV | Server returns a CSV with a header row | Not Run
ATD-RUN-04 | Unauthorized | No token rejected | 1. Call /atd/runs with no Bearer token | Returns HTTP 401 | Not Run

## Environments
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ATD-ENV-01 | List | Environments load | 1. Open Environments | Grid + API list the configured env(s) | Not Run
ATD-ENV-02 | CRUD | Create + delete | 1. New Environment 2. Delete it | Create + delete round-trip succeeds | Not Run
ATD-ENV-03 | In-use guard | Delete env used by a job | 1. Delete an env referenced by a job | Rejected with HTTP 400 (boundary) | Not Run

## Targets
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ATD-TGT-01 | CRUD | Create + delete | 1. New Target 2. Delete it | Create + delete round-trip succeeds; grid renders | Not Run

## Runner Settings
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ATD-CFG-01 | List | Settings load | 1. Open Runner Settings | Operational settings render with per-type inputs | Not Run
ATD-CFG-02 | Edit | Setting persists | 1. Change a setting → Save | Value persists with updatedBy; runner reads it at startup | Not Run
ATD-CFG-03 | Secrets masked | No secret leaked | 1. Read /atd/config | Secret values are never returned in clear (masked) | Not Run

## Cross-cutting
Test ID | Function | Test Scenario | Steps | Expected Result | Status | Tested By | Test Date | Comments / Defect Ref
ATD-XCT-01 | Language | EN ↔ AR RTL | 1. Switch language to Arabic | Shell flips RTL with Arabic labels; back to EN | Not Run